Copyright © 1999-2008 State of Kansas.  All rights reserved.

Project

Management

Methodology

Permission to view, use, and copy this material for personal

use is hereby granted, provided:  1)  The document is used

for informational purposes only.  2) The document is used

for non-commercial purposes only.  3) The document

includes the above copyright notice and this permission

notice appears in all copies.

CLOSE-OUT

EXECUTION

STARTUP

PLANNING

CONCEPT

Project Management Methodology

Release: 2.3

FSR Release 2.4

Planning is the Seed for Success

Without a project plan, project success will be difficult.  Team members would have limited understanding of expectations, activities may not be properly defined, and resource requirements may not be understood.

This section defines the elements of a project plan. As in all other parts of the ITEC Project Management Methodology, information contained in this section is intended as a starting point and has been kept to a general level to allow agencies to add requirements for project planning for specific projects.

This section provides an overview of planning and focuses on the project plan elements.

Responsibilities

The responsibilities for project planning are summarized below:

- Project Managers are responsible for developing the project plan for a specific project.

- State organizations are responsible for developing internal procedures to ensure that the planning process is completed consistently with the state organization’s business plan.  IT projects must be well thought out, support the key stakeholder goals, and include processes that allow the project to be tracked and controlled until completion.

- State organizations are also responsible for ensuring that there are adequate resources assigned to managing a project.  Management costs should not rolled into overhead costs. Management is a full time job for most projects.  It is an activity which requires training, focus and appropriate management and communication skills.

Terminology

As with all the sections of this methodology, a full glossary of terms is provided in Appendix A: Glossary; however, a sub-set of terms relative to this section includes:

- Activity is a task or series of tasks performed over a defined period of time.

- Budget refers to an estimate of funds planned to cover a project or specified period of future time.

- Configuration Management includes the processes, procedures, and tools to control project deliverable(s) in terms of release and revision and the system of procedures that monitors emerging project scope against the scope baseline. Documentation and management approval are required on any change to the baseline.

- Project Plan is a management summary document that gives the essentials of a project in terms of its objectives, justification, and how the objectives are to be achieved. It describes how major activities of the project management function are to be accomplished, and describes methods of  overall project control. The project plan evolves through successive stages of the project life cycle.

- Quality is a composite of attributes (including performance features and characteristics) of the product, process, or service required to satisfy the need for which the project is undertaken.

- Resource is something that lies ready for use or that can be drawn upon for aid or to take care of a need.

- Resource Planning is the identification of components required to complete the project.

- Requirements something essential to the existence or occurrence of something else.

- Risk is any factor that potentially can jeopardize the successful completion of a project.

- Risk Management is the art and science of identifying, analyzing, and responding to risk factors throughout the life of a project.

- Stakeholders are individuals or organizational entities whose stake in the project is sufficient for them to play an influential role in effecting the outcome of the project.

- Work Breakdown Structure is a division of tasks that organize, define, and graphically display the work to be accomplished to achieve the specified product.

What is Project Planning?

Project planning defines the project activities and describes how the activities will be accomplished. The purpose of project planning is to define each task, estimate the time and resources required, and provide a framework for management review and control. The project planning activities and goals include defining:

- The specific work to be performed and goals that define the project

- Estimates to be documented for planning, tracking, and controlling the project

- Commitments that are planned, and agreed to by stakeholders

- Project alternatives, assumptions, constraints and risks.

The planning process includes steps to estimate the size of the project, to estimate the resources required to complete the project, to produce a schedule, to identify and assess risks, and to negotiate commitments.

Repetition of these steps is necessary to establish the project plan. Typically, several iterations of the planning process are performed before a plan is completed.

The Planning Process

The planning processes discussed in this document are conducted to ensure successful implementation of project activities.  The planning process includes a group of related methods and techniques that provides the basis of defining a detailed list of activities that are to be completed, and how the work will get done, by whom, when, and for how much.  In summary, the project plan provides the specifics of:

- WHAT (Objective, scope, and statement of work)

- WHAT-IF (Contingency Plans)

- HOW (Development approach, work breakdown structures, processes and procedures)

- WHO (Project organization and resource schedule)

- WHEN (Schedule and milestones)

- WHERE (Facilities required)

The planning process is graphically presented on the next page.

Overview of Planning Process

State of Kansas

Problem Statement

Project Structure

Phase/Act/Task

Deliverables

Phase/Act/Task

Del

Estim

Schedule

Activity Network

Resource

Approval

DOC

ATP

Project Control Process

Importance of the Project Plan

What is a Project Plan?

A project plan is a formal, written document that is used to prepare for, manage and control a project.

The project plan forms the basis for all management efforts associated with the project.  It is a document that is also expected to change over time.

A template for a project plan is provided in this documentation. The information associated with the plan evolves as the project moves through its various stages and is to be updated as new information unfolds about the project in the Execution Phase.

Steps in the Planning Process

The planning process consists of the following basic tasks:

- Define the problem, the objectives and the success factors.

- Define the approach used to solve the problem.

- Define and sequence the tasks to be performed.  Identify all deliverables associated with the project.

- Define the dependency relations between tasks.

- Define the organization used to execute the project

- Estimate the resources required to perform each task.

- Schedule all tasks to be performed.

- Define a budget for performing the tasks.

- Identify the known risks and suggested approaches to prevent or mitigate.

- Define the process used for ensuring quality.

- Define the process used for configuration management and project requirements.

These tasks are described in subsequent sections.

Develop Project Tasks

One of the most important parts of a project planning process is the definition of activities that will be undertaken as part of the project. Activity sequencing involves dividing the project into smaller, more manageable components or tasks and then specifying the order of completion. The list of activities is often called a Work Breakdown Structure (WBS). The goal is to integrate the WBS, the schedule, and the budget into a written plan.

The WBS reflects activities associated with overall project management, requirements, design, implementation, transition management, testing, training, installation, and maintenance.  The project manager is responsible for defining all top level tasks associated with a project and then further decomposing them as planning continues.

An activities list is typically shown in one of two ways.  It can be shown as an outline or it can be graphically presented.  Two samples of WBS are shown below.

1.0	MANAGEMENT

1.1	Finalize Plan  Project

1.1.1	Review Project Plan with Project Team

1.1.2	Update Project Plan to create baseline

1.2	Track Project

1.2.1	Prepare status reports

1.2.2	Collect/analyze project metrics

1.3	Perform Quality Activities

1.3.1	Finalize QA Plan

    - Conduct Reviews

    - Conduct Audits

    - Review and Act on Recommendations

1.4	Perform Configuration Management

1.4.1	Finalize CM Plan

1.4.2	Develop Project Library

1.4.3	Manage Change Board

    - Maintain Configuration Items

1.5	Report States

    - Schedule and conduct Status Meetings

    - Meet with Executive Management

    - Prepare Staff evaluations

1.6	Conduct Close-Out Activities

    - Finalize User Sign-off

    - Conduct Lessons Learned

    - Document PIER

    - Archive Records

    - Celebrate Success

2.0	DESIGN

- 2.1	Prepare Preliminary Design

2.1.1	Develop Enterprise Architecture

2.1.2	Prepare Data Flow Diagrams

2.1.3	Prepare Logical Data Model

- 2.2	Prepare Detailed Design

2.2.1	Prepare Physical  Data Model

2.2.2	Prepare Data Dictionary

2.3	Document Design

2.3.1	Develop Design Specification

- 2.4	Review Design

3.0	DEVELOPMENT/INTEGRATION

3.1	Develop Software

3.1.1	Develop Server Application

3.1.2	Develop User Interface

3.1.3	Develop XYZ Interface

3.2	Procure Hardware

3.2.1	Procure Server

3.2.2	Procure Workstations

3.3	Procure Software Packages

3.3.1	Procure Database

3.3.2	Procure User Interface Building Tool

3.3.3	Procure Operating System

3.4	Perform Integration Testing

3.5	Convert Data

3.5.1	Develop Conversion Plan

3.6	Develop User Manual

3.7	Transition Management

4.0	ACCEPTANCE TESTING

4.1	Plan Acceptance Test

4.2	Conduct Acceptance Test

4.3	Develop Test Report

5.0	INSTALLATION

5.1	Develop Installation Plan

5.2	Site Preparation

5.3	Install at Locations

5.3.1	Headquarters

5.3.2	Site 1

Sometimes, instead of depicting the WBS as an outline, it is shown graphically, as below:

WBS

Define Project Tasks

WBS tasks are developed by asking,  “What tasks need to be done to accomplish the project objective?”  The choice of WBS structure is subjective and reflects the preferences and judgment of the project manager.

As levels of the WBS become lower, the scope, complexity, and cost of each subtask become smaller. The lowest level tasks, or work packages, are independent, manageable units that are planned, budgeted, scheduled, and controlled on their own.

As efforts of similar scope and type are planned, the basic WBS tasks remain fairly similar, but each project requires a specific set of tasks that address the uniqueness of the project's requirements.  Certain top level elements, such as project management, are included in the WBS of every project, regardless of its type, size, or complexity. Other items, like installation, may not apply to every project.

There is no simple formula to define how detailed a work breakdown needs to look.  There are, however, some helpful guidelines for completion:

•	Break down the work until accurate estimates of cost and resources needed to perform the task are provided.

•	Ensure that clearly defined starting and ending events are defined for the task.  This may correspond to the production of a deliverable or the occurrence of an event.

• 	Verify that the lowest level tasks can be performed within a “reasonable” period of time.  If the time period to complete a task is too long, an accurate project status in the implementation phase may not be possible. An industry standard rule of thumb is to make work packages that can be completed in timeframes of two weeks.

•	Verify that people assigned to the project are all assigned a WBS task.  Have a firm rule: if the task is not on the WBS, it is not worked on.

The WBS evolves over the course of planning.  It is highly probable that it will look quite different as the scheduling, estimation, and resource allocation portions of the plan are completed.

The WBS has multiple uses. It is both a task list for planning and a structure for providing report status during the implementation phase. As individual low level tasks are completed, the project progress is assessed. It also serves as a useful management communication tool by which results can be compared with expectations.

Define Project Development Phases

One of the difficult parts of talking about IT projects generically, is the wide range of such projects. Typically, in a small project, there is a single project development phase. In large or complex systems, however, there are often multiple development phases, where different functional requirements are met.

Sometimes these phases are driven by the need to achieve certain levels of functionality prior to the availability of the complete system. Other times, the phases are defined to partition the development effort and to reduce the risks associated with larger project efforts.

For large systems, the decomposition of the system into smaller components needs to be done early in the planning cycle. The rationale for the decomposition must be known, otherwise, different results derived from different reasons for the system decomposition may occur. For example, if a phase is defined to accommodate user needs, the phase may cross multiple functional areas of the system. If, on the other hand, a system is divided into phases simply to reduce risk, a functional division might occur where the phases represent completion of entire functional areas of the system. The way in which the phases are handled differs with each application. Often, phases are handled as top level WBS elements, with tasks associated with each phase defined.

Define Task Relationships

If a project is broken down into phases, be sure that the WBS reflects this. The WBS structure denotes a hierarchy of task relationships.  Subtask completion eventually rolls up into task completion, which ultimately results in project completion.  There can, however, also be relationships between tasks that are not within the outlined hierarchy. These relationships need to be noted, and the ultimate structuring of the tasks optimized to favor a minimum of horizontal dependencies and relationships. If the tasks are not organized efficiently, it becomes difficult to schedule and allocate resources to the tasks.

Defining Deliverables

Deliverables associated with each task are shown in the WBS and are reflected in the Work Product Identification (WPI)  portion of the Project Plan. A sample of a WPI template is shown below. All deliverables are listed as they are developed.  As the schedule is completed, the due date is filled in, and responsibility for the deliverable is assigned as it is known (typically when the organization chart is defined). The date delivered is a field that is filled in as deliveries are made.

Over the course of the project, a comparison of the due date and the date delivered provides a metric for how well deliverable dates are met by the project team.

Work Product Identification

| Product Name | Due Date | Date Delivered | Author/ POC |
| --- | --- | --- | --- |
| Requirement Specification | 4/1/96 | 4/1/96 | G. Brown |
| Design Specification | 8/1/96 |  | G. Brown |
| Test Plan | 8/1/96 |  | A. Jones |
| Implementation Plan | 11/1/96 |  | B. White |
| Source Code | 12/1/96 |  | L. Brass |
| Test Report | 1/30/97 |  | A. Jones |

While the deliverables list is a compilation of information identified in the WBS and the project schedule, it is useful to maintain a separate list since deliverable completion can be a key metric of project progress.  Separate tracking of deliverables can help keep a project on track.  It also serves as a useful communication tool with the Steering Committee and the project team.

Overview of Project Budgeting

Paralleling the development of the schedule is the development of a budget. At the initial stages of project planning, budgeting is the determination of costs associated with the defined activities. The steps associated with budgeting are highly dependent on the estimated length of tasks and the resources assigned to the project.

Budget estimates are refined in the planning process until they are baselined at project start-up. Budgeting serves as a control mechanism where actual costs can be compared to the budget.  The budget is often a set parameter in the execution of the project.  When a schedule begins to slip, cost is proportionally affected.  When project costs begin to escalate, revisit the project plan to determine whether scope, budget, or schedule needs adjusting.

Identify Cost Factors

To develop the budget, the applicable cost factors associated with the project tasks are identified. The development of costs for each task should be simple and direct and consist of labor, material, and other direct costs. Cost of performing a task is directly related to the personnel assigned to the task, the duration of the task, and the cost of any non-labor items required by the task.

Generally budget estimates are obtained from the people responsible for managing the work efforts.  This provides the expertise required to make the estimate and provides buy-in and accountability during the actual performance of the task.

Determining how long the task takes is the single most difficult part of deriving a cost estimate. The labor costs should factor in vacation time, sick leave, breaks, meetings , and other day-to-day activities.  Not including these factors jeopardizes both scheduling and cost estimates.

In calculating the cost of labor, be certain to burden the costs appropriately for your organization. Burdened cost typically refers to the overhead and general expenses associated with an employee. These costs are beyond strict salary expenses (e.g., office space, benefits, etc.).

Non-labor charges include such items as material costs, reproduction, travel, cost of capital (if leasing equipment), computer center charges, and equipment costs.

Project Estimate Summary Worksheet

For large systems, a project management tool is typically preferred for cost estimation. A Project Estimate Summary worksheet is another appropriate model for costing and can be useful if completed prior to entering information into a tool. Tasks included in this sample should be tailored to specific project cases.

Costs are assigned to the lowest level WBS work package task. These costs are then combined to determine a sub-task cost. In turn, these are combined to determine the overall task cost, which can be summed to find the total project cost.

Instructions

The basic component of the Project Estimate Summary Worksheet is the task number.

- Task Number

The number corresponds to the activity number reflected on the activity list and schedule.  The numbering sequence is an outline format.  Few projects require lower than three levels of sub-tasking.  Each task structure should include deliverables and milestones.

| Project Tasks |  |
| --- | --- |
| 1. | Task |
| 1.1 | Sub-Task |
| 1.1.1 | Work Package or second level of sub-task |
| 1.1.1.1 | Third level |

- Task and Activity Name

The project’s task and activity name is a brief description. Example:  “Plan Training,” “Design System.”  Longer descriptive narratives are included in the activity analysis.  This description should reflect the same information shown on the activity list and schedule.  The number of hours and cost of the lowest level task.

| Project Tasks |  |
| --- | --- |
| 1. | Project Design |
| 1.1 | Develop Functional Specifications |
| 1.2 | Develop System Architecture |
| 1.3 | Develop Preliminary Design Specification |

The remainder of the columns pertain to cost and hour details relative to a specific activity. The cost categories include: labor, material, travel and other.

Always start your cost analysis at the lowest level and total the lowest level tasks to the next level.  All “x.x.x” would be added together to determine the value of “x.x” and all “x.x” level tasks would be totaled for “x” level.  Finally, all “x” level totals would be totaled to get  project total.

The project may require more than one line to complete the budget when multiple salary rates used to determine “labor cost” for an activity.  Labor cost is derived by multiplying labor hours by the labor rate.  The project manager may either use an aggregate rate or specific multiple rates.   The costs for each task should be totaled and put in “Total per Task.”

At the end of the form is a line for risk totals.  Risk allowances are added to the project in terms of Schedule (adding more time) and Cost (adding additional cost to estimates).  A project manager can do this in two ways: adding time and/or cost at the activity level; or adding time and/or cost at the end of the project.  This information should come from your Risk Analysis Worksheet which will be discussed in subsequent sections.

See the following page for a sample of a Project Estimate Worksheet.

Project Estimate Summary Worksheet – Sample

| Customer: KDOT | Prepared by: H.A.T. |
| --- | --- |
| Project: MGT System | Date: 9-9-1999 |

| WBS | Project Task | Labor Hour | Labor Rate | Labor Cost | Material Cost | Travel Cost | Other Cost | Total per Task |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | : |  |  |  |  |  |  |  |
| 5.0 | Define Requirements |  |  |  |  |  |  |  |
| 5.1 | Define Functional Requirements |  |  |  |  |  |  |  |
| 5.1.1 | Conduct JAD Sessions |  |  |  |  |  |  |  |
| 5.1.1.1 | Schedule Sessions | 8 | 30 | 240 |  |  |  | 240 |
| 5.1.1.2 | Prepare for Sessions | 24 | 40 | 960 |  |  |  | 960 |
| 5.1.1.3 | Facilitate Meetings | 24 | 40 | 960 |  |  |  | 960 |
| 5.1.1.4 | Attend and Participate | 240 | 38 | 9120 |  | 2000 |  | 11120 |
| 5.1.1.5 | Document JAD Meetings | 24 | 30 | 720 |  |  |  | 720 |
| 5.1.2 | Prepare JAD Document |  |  |  |  |  |  |  |
| 5.1.2.1 | Prepare Documents for Review | 80 | 40 | 3200 |  |  |  | 3200 |
| 5.1.2.2 | Schedule Review Meetings and Distribute Document | 8 | 30 |  |  |  |  |  |
| 5.1.2.3 | Review the Documents | 80 | 38 | 3040 |  | 500 |  | 3540 |
| 5.1.2.4 | Meet to Gain Sign-off | 40 | 39* | 1560 |  |  |  | 1560 |
| 5.2 | Define Technical Requirements |  |  |  |  |  |  |  |
| 5.2.1 | Review KSA documents | 16 | 42 | 672 |  |  |  | 672 |
| 5.2.2 | Review Current System Architecture | 16 | 42 | 672 |  |  |  | 672 |
| 5.2.3 | Review AITMB Plan | 16 | 42 | 672 |  |  |  | 672 |
| 5.2.4 | Document Interface Points | 8 | 42 | 336 |  |  |  | 336 |
| 5.2.5 | Document the Technical Requirements for New Application | 16 | 42 | 672 |  |  |  | 672 |
| 5.2.6 | Review the Technical Requirements | 16 | 50 | 800 |  |  |  | 800 |
| 5.3 | Prepare Consolidated Requirements Documents | 8 | 42 | 336 | 300 |  |  | 636 |
|  | : |  |  |  |  |  |  |  |
|  | : |  |  |  |  |  |  |  |
| Other: |  |  |  |  |  |  |  |  |
| Sub-Totals: |  |  |  |  |  |  |  | 622,406 |
| Risk (Reserve) From Risk Analysis Worksheet |  |  |  |  |  |  |  | 76,120 |
| TOTAL (scheduled) |  |  |  |  |  |  |  | 698,526 |
| Comments: (List assumptions for costs as appropriate.) |  |  |  |  |  |  |  |  |
| * Blended Meeting Rate |  |  |  |  |  |  |  |  |

Document Assumptions

As with developing a project schedule, documenting assumptions made while developing the project budget is critical to the success of the project. Without clear documentation of these assumptions, tracking to the budget is very difficult and risky.

If, for example, a budget assumed that the material would be acquired at one price rate and only substantially higher cost material was available to perform the task, there would be a budget problem. If the assumption is not documented, the project manager may inadvertently increase project cost and may unwittingly jeopardize chances for the project’s success.

Review the Cost Estimates

Development of project budgets typically requires more than one person. Rarely does a single individual have the knowledge and understanding of all the factors affecting every aspect of a project.

Upon completion of a draft budget, interview the team and determine if the work descriptions, schedule and associated budgets are complete and reasonable. Determine if there is a common understanding of what it costs to do the tasks. Get independent estimates. Where there are significant differences, determine the reasons and either redefine the work packages, schedule, and budgets or review and reiterate the estimates.  The total labor days per phase should be checked against the rule of thumb that suggests the following distribution of development project effort and cost:

- 40% for planning and design

- 20% for development

- 40% for testing

It is extremely important to get buy-in on the budget from the people who will actually perform the work. Participation results in having a stake in the project's success and fosters accountability. Imposing budgets on staff without a buy-in may result in failure.

Estimated Cost at Completion Report

A sample of one type of budget report which would become part of the Project Plan is shown on the next page.

- Estimated Cost at Completion Summary

| Analysis in Hours |  |  |  |  |  |  |  | Analysis in Dollars |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS No. | Activity Description | Budget Hours | Actual Hours | Est. to Complete | Est. @ Complete | Variance (+ = More) | Budget $ |  | Actual $ | Est. to Complete | Est. @ Complete | Variance (+ = More) |  |
| 1.0 | Define Requirements | 430 | 0 | 430 | 430 | 0 | 17,780 |  | 0 | 17,780 | 17,780 | 0 |  |
| 2.0 | Prepare RFP | 572 | 0 | 572 | 572 | 0 | 22,880 |  | 0 | 22,880 | 22,880 | 0 |  |
| 3.0 | Issue RFP and Evaluate Vendors | 433 | 0 | 433 | 433 | 0 | 17,320 |  | 0 | 17,320 | 17,320 | 0 |  |
| 4.0 | Close-Out | 72 | 0 | 72 | 72 | 0 | 2,880 |  | 0 | 2,880 | 2,880 | 0 |  |
|  | TOTAL | 1,507 |  |  | 1,507 | 0 | 60,860 |  |  |  | 60,860 | 0 |  |

The Estimated Cost at Completion Summary is also used as a reporting document to the Steering Committee and will be discussed in the Execution Phase of this methodology.

Configuration Management

Within the general IT industry, neither the use nor the meaning of configuration management terms have been standardized. For the purposes of this document, the following terms apply to Configuration Management:

Change control is the process of controlling, documenting, and storing the changes to control items. This includes proposing the change, evaluating it, approving or rejecting it, scheduling it, and tracking it.

Configuration Management are processes including procedures and tools to control project deliverable(s) in terms of release and revision, to monitor project scope against the baseline, and manage approval on any change to the baseline.

Control item is a project element that is considered a unit for the purpose of configuration management.  This includes such things as software modules, versions of software systems, the project design document, the project plans, and so forth.

Version control is a method used to control the release and installation of software versions. This includes recording and saving each release and documenting the differences between the releases. Version control applies not only to developed software, but also to off-the-shelf software systems that are used as part of the project.

Configuration Management Organization

Effective configuration management requires an effective and well-defined configuration management organization.  The configuration organization is responsible for:

- Defining who will be responsible for and have authority over configuration management processes.

- Setting standards, procedures, and guidelines  for the full project team to follow.

- Defining tools, resources, and facilities to be used for configuration management.

This information is summarized in either a standard state organization configuration management policy manual and/or in the project Configuration Management Plan.  The detailed configuration management  information is represented as a summary in the Project Management Plan. The relationship of  the configuration management summary in the Project Management Plan and the detailed Configuration Management Plan is depicted in the figure on the following page.

- Project Management Configuration Management Summary

Configuration Management Plan

A sample Configuration Management Plan outline is shown below.

Sample Outline for a Configuration Management Plan

1.	Configuration Management organization and resources

1.1	Organization structure

1.2	Personnel skill level and qualifications

1.3	Facilities needed

1.4	Equipment and tools used

2.	Standards, procedures, policies, and guidelines

2.1	Diagram of information flow

2.2	Parameter for the automated tools sets

3.	Configuration identification

3.1	Method for defining control item

3.2	Method for configuration control

3.3	List of control items

4.	Identification methods

(Naming and marking of document, software components, revisions, releases, etc.)

5.	Submission and retrieval of control items

6.	Version control

6.1	Preparation of software and documentation versions

6.2	Release approval procedure

7.	Storage handling and delivery of project media

Storage requirements (both automated and paper)

8.	Relationship to contractor configuration management (include 	their plan and procedures if separate from state's processes)

9.	Other information

Tasks During the Planning Phase

During the planning process, the project manager defines the group or persons responsible for project configuration management and defines the procedure and required resources for performing configuration management. During the planning phase, the project team also identifies the control items.  The goal is to:

- Explicitly assign configuration management’s authority and responsibility for the project.

- Ensure that configuration management is implemented throughout the project’s life cycle by setting standards, procedures, and guidelines  that are produced and distributed to the full project team.

- Ensure that project management has a repository for storing configuration items and associated configuration management records.

- Ensure that QA reviews the baselines and configuration management activities on a regular basis.

Relationship to Quality Management

Many of the issues related to configuration management are similar to the issues related to developing a project’s quality system. In fact, in software development projects, many of the tasks for quality and configuration management overlap. For this reason, a clear definition needs to be established, even at the planning stage, as to who will play what role.

Authority and Responsibility

Every project includes some level of development or integration activity that requires configuration management.  Projects need to include at least a manual configuration control process for storing, retrieving, and changing project requirements and management documents. The responsibility for configuration management is assigned in the project plan.

The configuration management authority and responsibility can be handled in one of two ways:

- The state organization maintains a standard, enterprise-wide approach to configuration management and has an identified group responsible for these tasks on all projects undertaken; or

- The project develops a sub-team within the project management structure to perform the configuration management. This team may be assigned to the project on a full-time or part-time basis depending on the size of the project.

In either case, both the authority and the responsibility for all roles and activities must be clearly defined.

Configuration Elements

During the early stages of project planning, the person responsible for configuration management and the project manager defines the elements placed under configuration control. The list of control items is not standard. The best place to start is with the Activity List and Work Breakdown Structure. Typically, all major deliverables are controlled. The actual software and hardware elements are also controlled.

Some of the more specific considerations include:

- Hardware configuration, system architecture, and communication diagrams.

- Software, code, design documents, testing plan, and software review data.

- The Project Management Plan (schedules, budgets, contracts), support function plans, and correspondence and other documents necessary to recreate a project.

Configuration Management Procedures

Procedures and tools are necessary to ensure successful implementation of a configuration management process.

The plan also contains information on how the detailed procedures will be developed and specifies that these procedures are in place by project start-up.  Some key processes to be addressed in the procedures include:

- How do developers and project team members request and retrieve configuration control items?

- What are the numbering, sequencing, and data processes to be used?

- Does the project contain sensitive or security-driven data; if so, will the configuration management meet the control requirements for this data?

- Where is the location of controlled items, and how does the project team get access to them?

- What items will be placed under automated control and what items will be manually controlled?

- Will there be a change control board to determine when changes will be allowed, and how will this interface with the other configuration management procedures?

- What is the relationship to the quality team if these functions are not performed by the same group?

The plan may also include diagrams and flow charts to describe procedures for submitting change requests and for reporting problems.

Configuration Management Process Flow

The following figure portrays an overall flow of control items within a configuration management framework.  In the figure, CSIA refers to Cost/Schedule Impact Analysis.  A CSIA is a detailed analysis of what the change might cost and, if implemented, what impact it might have on the project schedule.  See Section 5, Change and Issue Management, for a more detailed description of this process.

Control Item Flow within a Project

Storage of Control Items

Ensure that the Project has a repository for storing Configuration Items and associated Configuration Management Records.

The configuration management environment includes the resources necessary for the implementation of the configuration plan. This includes:

- Configuration control tools:

- Automatic version control and change control tools.

- Monitoring, reviewing, and registration of support utilities.

- Storage facilities -- a safe repository for all approved configuration items, including:

- On-site automated storage for the day-to-day development process.

- On-site paper storage for the day-to-day project for configuration control items that are not stored in automated form.

- Off-site storage for disaster recovery.

Configuration Management is one area in which many automated tools exist. Automated configuration control is best when used in a multi-user development environment, such as a LAN, to facilitate the sharing of project information and data and to allow for consistent application of the configuration management procedures. Controlled elements can be stored in a central database, and developer access is managed from a central configuration control system. Without such a system, added manual controls and additional tasks for the developers may need to be imposed. Multi-location development is another environment that could be more easily handled with automated tools.

Configuration Management Goes Beyond Development

Configuration management is a process that continues beyond the project development cycle and into the maintenance and operation phases. A project that has clearly implemented a successful configuration management process adds to the value of the system once it reaches maintenance.

Overview of Project Scheduling

Following the definition of project activities, the activities are associated with time to create a project schedule. The project schedule provides a graphical representation of predicted tasks, milestones, dependencies, resource requirements, task duration, and deadlines. The project’s master schedule interrelates all tasks on a common time scale. The project schedule should be detailed enough to show each WBS task to be performed, the name of the persons responsible for completing the task, the start and end date of each task, and the expected duration of the task.

Like the development of each of the project plan components, developing a schedule is an iterative process. Milestones may suggest additional tasks, tasks may require additional resources, and task completion may be measured by additional milestones.  For large, complex projects, detailed sub-schedules may be required to show an adequate level of detail.

During the life of the project, actual progress is frequently compared with the original schedule. This allows for evaluation of development activities. The accuracy of the planning process can also be assessed.

Basic efforts associated with developing a project schedule include the following:

- Define the type of schedule

- Define precise and measurable milestones

- Define all tasks and sub-task

- Estimate task duration

- Define priorities

- Define the critical path

- Document task relationships

- Document assumptions

- Identify risks

- Review results

Define the Type of Schedule

The type of schedule associated with a project relates to the complexity of the implementation. For large, complex projects with a multitude of interrelated tasks, a PERT chart may be used. PERT charts depict interdependencies and associations and allow planning to include these relationships. A key feature of the PERT method is the ability both to determine and to show the critical path of the project (see later sections for a discussion of critical path). A sample PERT chart is shown below.

Sample PERT Chart

For small projects, a GANTT chart (or bar graph) is adequate. These schedules are two-dimensional representations that show the tasks and the timeframe for completion. Since task interrelationships are not easily shown on a GANTT chart, it is considered a weak planning tool for very complex information technology projects. However, the GANTT chart is very common for reporting status and for defining the schedule.  A sample GANTT follows.

- Sample GANTT Chart

Define Precise and Measurable Milestones

Key events are often denoted by milestones. These events typically have no duration. For example, deliverables often are represented as milestones, while the effort to produce the deliverable is referred to as a task.

While milestones are unique to each project, some example project milestones are shown below:

- Requirements Approval

- Phase Review Approval

- Prototype Approval

- Design Reviews Complete

- Code Reviews Complete

- Unit Test Complete

- Integration Test Complete

- Acceptance Test Complete

- System Acceptance by User

- Hardware Shipment

- Documentation Delivery

Milestones can occur at the end of each work package in the WBS and serve as a measurable item upon which to base success of a task. Major project milestones should be summarized and included in the summary project plan.

For contracted work, milestones are often used as a point in the project where interim payments might be made. If this approach is used, mutual agreement is necessary on the content of each milestone and the cost associated with that milestone.

Estimate Task Duration

Estimating task duration is one of the most challenging aspects of project planning. It is also a key to later cost estimation. This is a refined process that occurs throughout the planning process, as it is directly affected  by results of the staffing and costing activities.

With defined task durations, the team knows what to expect and what is expected of them. A task duration is rarely overestimated, but is frequently underestimated. Inaccurate estimates can result in an increase in the "frenzy level" of a project. The frenzy escalates as sponsors scramble for more money, and/or the technical staff scramble to complete a project in an unrealistic timeframe. Often, the end result is cutting corners, excessive overtime, and a dissatisfied user.

The estimation process is complex because activity duration is affected by numerous variables that must be dealt with concurrently in the planning phase. Some of these variables include staff availability, the skill level of the person assigned to the task, unexpected events, efficiency of work time, and mistakes and misunderstandings during the development of the project plan.

When estimating the duration of a task, reality is a major factor. The knowledgeable scheduler takes into account absenteeism, meetings, discussions, and interaction among the staff. No one is 100% productive every hour of the workday. If a scheduled task assumes 100% productivity, the schedule rapidly falls apart. A successful schedule builds these types of factors into the duration estimate.

There are several techniques that support task duration estimation. The most common technique is based on the historical experience of a similar scope of work performed by the estimator. Collected and archived historical project data are used successfully by many organizations to achieve quality performance on project deliveries.  The database of Post Implementation Evaluation Reports maintained by the Kansas Information Technology Office should have a wide range of project schedules to review in developing your project schedule.

Historical records greatly support both the duration and the cost estimations that are so important in this phase. Data based on staff skills are far more valuable than generalized “industry” estimates. If historical data does not exist, seek the advice of experts and others who have completed similar tasks.

When historical data or experts are not available, use a technique of getting estimates from multiple sources, comparing results and estimating the duration based on the multiple inputs. The nature of this method is predicated on finding good sources for providing the estimates.

Define Priorities

Clearly defining the task priorities helps to resolve any scheduling and/or resource conflicts. Understanding the priorities and relationships of the tasks assists in resolving difficult scheduling conflicts.

Define the Critical Path

The critical path is the longest path through a project. It determines the earliest possible completion of the work. The critical path is carefully managed because if critical path tasks slip, the entire project is delayed. In order to manage the project, the project manager determines the critical path and remains aware of its importance throughout the implementation of the plan.

The successful scheduler considers availability of both labor and non-labor resources.  Equipment availability on a long lead item often drives the critical path of a schedule. If installation equipment is required, for example, and the equipment cannot be delivered for six months, the installation phase is held up for that period of time.

Document Task Relationship

After the WBS has been created, the tasks of each major section should be ordered into their logical sequence.  Then, if tasks are dependent on each other, the task dependencies should be indicated.  That is, if one task must be completed before another, then the first is a predecessor to the second, and the second task is a successor to the first.  This relationship would be a Finish-to-Start relationship, i.e., the first task must finish before the second task can begin.

Other task relationships include:

- Start-to-Finish:  this task must start before the previous one can finish

- Start-to-Start:  this task must start at the same time as the other task

- Finish-to-Finish:  this task must finish at the same time as the other task.

Document Assumptions

Documentation of the assumptions made in developing the project schedule are critical to the later success of the project. Without clear documentation of these assumptions, later changes to the schedule are very difficult and risky.

If, for example, a schedule was shortened because it was assumed that a highly skilled person would be performing the work, that assumption should be documented. Then, if a less skilled person is actually assigned to perform the task, the project manager can recognize the risk and make necessary changes and decisions. Without documentation of the assumption, the schedule could be later placed in serious risk without the project manager realizing it.

Review the Results

The development of a schedule requires input from more than one person. No one possesses all the knowledge or understanding of all the factors that affect schedules in every aspect of a project. Schedule review also prompts buy-in to the schedule.

Once an initial cut at the schedule is ready, a team should perform a review. The work descriptions and the schedule should be reviewed by the people named to do the work.

Determine if there is a common understanding of what has to be done. Get their independent estimates as to how long it will take to do the job.  Where there are significant differences between the current schedule and new estimates, review and revise the schedule estimates.

Scheduling Tools

There are numerous tools that support the development of project schedules. Many of these tools prepare either a GANTT or PERT chart. They require experience in setting up the projects and in defining task relationships and dependencies.

Each state organization should select tools that best meet their needs.

References

The project schedule is included as an item in the Project Management Plan. Since output from many scheduling programs does not effectively integrate into word processing documents, it is assumed that the schedule will be created separately from the word processing template. The plan should include a reference to the most current, baselined electronic version of the schedule.

Quality Process

The quality plan identifies the procedures and activities that the project team defines, plans for, and executes for quality. A quality model should be maintained by each state organization, and this model should describe the detailed quality procedures that are used for IT projects. The following model defines a quality assurance process that is consistent with ISO (International Standards Organization) 9000 standards.

Quality Assurance Model

Plan and Manage

Quality Assurance

Creating the Quality Plan

The state organization’s quality model should be based on standards and procedures that enable the quality manager to ensure quality throughout the life of the project by:

- enforcing quality standards and procedures through formal reviews, walkthroughs, and inspections

- tracking and reviewing defects at each phase of the project.

Sometimes projects will not require a “unique” quality plan, but can be completed under the standard process.  For large, lengthy or complex projects requiring a unique Quality Plan, it defines, tracks, and measures the project’s quality goals. The Quality Plan describes how the project implements its quality process and defines the processes that will be taken to prevent and remove defects. It is important for management to consider the quality goals early in the project and ensure that quality activities are integrated into the overall project management plan.

The quality plan identifies the person who is responsible for the quality assurance activities, identifies the scheduled quality activities, and identifies the resources required to conduct the activities. Quality activities are included in the project schedule as milestones and quality audits that require budgeting and staffing.

Successful quality processes always strive to see quality through the eyes of the customer. The customer is the ultimate judge of the quality of the product they receive. They will typically judge a project by whether or not their requirements are met. To ensure delivery of a quality product, each phase of the project should ensure that requirements are addressed.

It is important to include a process that validates that the currently defined requirements will be satisfactory to the customer. It is counterproductive to develop a system that meets a documented requirement if you and the user know that the requirement has changed. The change management process helps to control the number of such changes, but quality processes must be in place in order to make changes when they are necessary.

Responsibility for Quality

Though the Project Manager has overall responsibility for the quality of the final product, every project member needs to buy-in to the responsibility for producing a quality product. Through ownership of the organization’s quality policy, the individual team members become the most effective way to implement quality into products efficiently and completely. A quality policy cannot rely on “adding” quality at the end of a process; it must be built into the work of each individual on the team. It is far more cost effective to have team members add quality into their day-to-day jobs than to have a quality analyst find a problem after a process has been completed.

Independence of the Quality Assurance Team

While it is important that each team member be responsible for the quality execution of tasks, a quality team is typically included in the project team. The team assures that the quality plan is executed as planned. As an organization’s quality processes mature, the need for the external quality unit decreases.  This quality team reports functionally to the Project Manager, but must also have a reporting chain outside the project to facilitate problem escalation.  Problem escalation is the process of moving a problem to a higher management level if sufficient attention is not given by the project manager.  The independent reporting chain provides a check and balance on the project.

Checklist

Quality checklists are often developed as part of the quality procedure definitions. The checklists and associated quality procedures are developed individually by each state organization.

References

The quality plan overview for the project is included in the Project Management Plan.

Importance of Project Requirements

Requirements definition is one of the most crucial steps in the process of creating a project. Without well-defined requirements, managers cannot plan a project, developers and integrators do not know what to build, customers do not know what to expect, and there is no way to validate that the system as built satisfies the needs of the organization.

What is a Requirements Process?

The disciplined application of proven methods and tools to describe a proposed system's intended behavior and its associated constraints.

When are Requirements Defined?

System requirements evolve over time. At each stage of the project, additional information is derived and documented. At the onset of the concept phase, for instance, basic business needs are expressed and documented.  Over time, these needs are refined and developed into functional user requirements and are later developed into detailed technical specifications.

During project planning, requirements must be understood in enough detail to develop project budgets and define resources needed to implement the solution. Requirements are reviewed, the project team strives to understand the requirements, and the requirements are refined further, if necessary.

A project team should never commit to the project activities list, schedule, or budget to build something unless it is well defined. If requirements will be defined in later stages of a development effort, the final, detailed project plan can only cover that portion of the project where the requirements are defined.

At project startup, requirements are reviewed to ensure that they are clear and that the development team has a full understanding of the requirements. Areas where additional definition is required are noted and logged as action items.

During the design phase, detailed design specifications are developed based upon the functional requirements and the defined scope of the project. These detailed specifications are used to define the specific technical approach and implementation that will be used to fulfill system requirements.

Requirements Specifications

The requirements specifications involve many layers of specification, but starts with a Business Needs Identification Statement. This is a very high level document that describes the top level needs that the system must meet. The statements are high level and may be met by a combination of automated and manual processes. For example, a Business Needs Requirement might be: “The system must support timely payment of invoices.”

A functional specification describes the hardware and software requirements needed to perform defined functions. It is based upon the Business Needs Statement and further defines those business needs into technical requirements. The functional requirements express more specifically how business needs might be met. For example: “Invoices must be created weekly based on input received from the order processing system.”

The functional specification defines requirements in terms of inputs, outputs, and behavior of the system. External interfaces are also defined. Non-functional requirements and constraints, such as performance, portability, standards compliance, and reliability are also defined in a functional specification.

Who Defines Requirements?

Requirements definition is a difficult task. People often have difficulty expressing needs without immediately attempting to define the solution. It is also difficult to conceptualize how new automation will affect a task that is currently being done manually or with older technology.

Requirements definition is also a communication intensive process, and, unfortunately, technologists and subject matter experts have different vocabularies, backgrounds, and preferences. This makes the specification process difficult.

To successfully define the requirements of a system, the requirements process includes, and is focused on, the intended users. There are various techniques that can be used to derive the requirements, including interviewing users, observing users conducting their tasks, and holding Joint Application Design (JAD) sessions, where users and analysts interactively explore requirements in a facilitated session.

For more complex systems and for projects with requirement definition issues, prototyping of user screens and reports can help facilitate the communication process. With a prototype, users can see samples of how the system operates, and the developers can provide detailed information that the user group can comprehend.

Requirements Traceability

The state organization will define processes for requirements traceability. The requirements traceability process ensures that the requirements defined in the functional specification are carried through the planning, execution, and testing phases. The traceability process involves the following steps:

Requirements traceability is facilitated by decomposing requirements from a document format to a list or table format. Often requirements that are not decomposed result in some ambiguities, such as:

- Multiple requirements may be embedded in a single sentence.

- Compound conditions to requirements may exist in a single sentence (i.e., and/or conditions).

- Requirements may not be testable as written.

- Requirements may be inconsistent.

By placing each requirement as an individual statement that can be tracked and accounted for, the project team can ensure that stated needs of the system can be traced. The first traceability occurs when the WBS is completed. Each requirement is reviewed to ensure that there is a task defined for fulfilling that requirement. Allocation of requirements to the WBS helps define the WBS element and indicates the scope of work covered by the item. This definition allows for a more careful estimate of schedule, budget, and resources in the planning phase.

A sample requirements traceability table is shown below:

Project Requirements

Project Traceability Table

Documents Product Specifications with appropriate cross-references to other documents.

Numbering each requirement  with a unique identifier further facilitates reference to the requirement for the purposes of contract, engineering, quality assurance, and project management. Quantifying non-testable requirements by adding clarification verbiage and assumptions facilitates the project over its life cycle.

Where appropriate, columns can also be added that assign the requirement to a category for sorting. Also, as the project progresses, there can be references to the test plans and procedures, and a compliance field can be entered to define which requirements have been fulfilled and tested.

This requirements analysis process allows specific requirements to be uniquely identified and serves as a common method between developers, customers, and the project management team. It facilitates general communication, traceability, and provides a method for controlling requirements changes.

Approvals

Requirements documents are approved by the project team, the users, and the Steering Committee.  Specifications are reviewed and baselined at the start of the project. Detailed specifications developed within the project execution phase are rebaselined at approval to incorporate changes to the project scope, of course, these changes must be approved by the Steering Committee.

Managing Requirements Changes

A change control process is developed to ensure that the requirements of a project do not change uncontrollably as discussed in Configuration Management.

References

The Requirements Traceability Table, i.e. Project Requirements,  is included in the Project Plan.

Overview of Resource Planning

Every organization has a limited number of resources to perform tasks. A project manager's primary role is to find a way to successfully execute a project within these resource constraints. Resource planning is comprised of establishing a team that possesses the skills required to perform the work, as well as scheduling the non-labor resources (tools, equipment, and processes) that enable the staff to complete the project.

Determining the Size of the Team

The optimal size of a project team is driven by two principal factors. One is the total number of tasks to be performed, and the other is the effort needed to perform the tasks.

In developing the schedule and assigning the resources, the project manager determines the optimal mix of staff to activities. Doubling resources does not necessarily double productivity. For example, 365 engineers could not complete in a day a project estimated at one person per year. At some point, people begin to get in each other’s way. The significance of the project duration, as well as each major activity's duration, needs to be clearly understood and documented as part of the scheduling process.

Adding more people to an activity creates the need for additional communication and may also increase the need for equipment or tools. Large teams require a significant amount of coordination and teamwork. Sometimes a smaller team can accomplish much more than a larger one in a shorter period of time. The optimal selection also depends on the personalities of the team members and the communication and organizational skills of the project manager.

Adequate and timely personnel planning contains cost overruns. Having personnel on-board when they are not essential is extremely costly. It is important for the project manager to understand the size of the required team needed to perform the work on a week by week basis.  For this reason, significant effort needs to be made in the planning phase to identify the resources required to complete each task.

Determining Required Skills

Finding available staff with the skills required to perform a task is critical to project success.  For example, some assumptions about the skills of the person performing the task are made by the project manager. The skills of the people performing the work is directly related to the time it takes to perform a task.

It is helpful in the planning process to develop a list of skills required.  This skills list may then be used to determine the type of personnel required for the task.

The project manager pragmatically assesses the skills of the available people on the project. The project manager’s job is to determine the risks associated with the available skills and to build a plan that realistically accounts for those skills. Unfortunately, skill level is not a yes/no factor. People have varying degrees of skill, and the manager needs to determine the level of schedule adjustment that should be made based upon the staff skill level.

Where staff with the necessary skills are largely unavailable for assignment on the project, the project manager and project sponsor has the option to hire the necessary talent or contract services to perform the work.

Identifying Required Non-Labor Assets

All project teams require the tools necessary to successfully perform the tasks assigned. In scheduling resources, the project manager must ensure that both people and necessary equipment are available simultaneously.

The need for adequate work space is often overlooked when planning a project. If a 15-person project team is going to start work, there needs to be a facility to house the staff. Ideally, the team should be placed in contiguous space to facilitate interaction and communication. By having everyone working in close proximity, chances for project success are increased. While this may not always be feasible, it is a goal worth striving for.

In addition to workspace, equipment for the team should be included in the plan. Assuring the availability of equipment at critical points in the project is key in planning a successful project.  Also, technical support for equipment and software should be identified at this point.  Efficiency and morale are negatively affected by non-availability of equipment information or support needed to perform a task.

Define Resource Profiles

A staffing plan is developed for each project.  (For small projects, this may be simply stated as the assignment of three people full time to the project throughout its six month duration.  For more significant projects, the staffing plan identifies when and how staff is brought onto and taken off the project team.)

The following chart and the graph on the following page are useful in the Project Plan for staffing large projects.

FTE Resource Loading

| POSITION | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SW Mgr | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Sr. SW Eng. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| SW Analyst | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 |
| Programmer |  |  | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |
| Config. Mgr |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Tech Writer | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |
| Support | 0.25 | 0.5 | 0.5 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 0.5 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3.75 | 4.5 | 7 | 8 | 8.5 | 7.25 | 7.25 | 7.25 | 7.25 | 7.25 | 8.5 | 7 |
| POSITION | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| SW Mgr | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Sr. SW Eng. | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| SW Analyst | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Programmer |  |  | 2 |  |  |  |  |  |  |  |  |  |
| Config Mgr |  |  | 1 |  |  |  |  |  |  |  |  |  |
| Tech Writer | 0.5 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Support | 0.25 | 0.25 | 0.5 |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL | 3.75 | 4.25 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

- Example Staffing Plan

The previous chart and graph illustrates the planned number of people required by week for a project team.  Both also depict how actuals might be applied in the performance of the project.

The graphic representation of the staffing plan helps to point out peaks and valleys in staffing that can present serious project management problems.  The project manager realistically determines how a relatively consistent staffing level can be maintained. Particular attention is paid to releasing resources when they are no longer needed on the project. It is unrealistic to assume that the project can go from a 5-person to 10-person level of effort in a month and then return to a 5-person effort in another month. Resource leveling is supported by many project scheduling tools, but requires the special attention of the project manager in both the planning and the execution phases of the project.

Forming the Team

Project organization is used to coordinate the activity of the team and to define the roles and responsibilities of team members. Project organization is needed for every IT project, and a project manager must always be identified.

Confusion and lack of productivity are the result of poor project organization. This is where many projects run into trouble. A good organization facilitates communication and clearly defines roles and responsibilities.

There are numerous ways to organize a project, and many projects require a unique organizational structure. There are no standard organizational methodologies that every project should use.  A sample organization chart for a large project is shown below, with the types of functions that are often assigned to a project.

- Sample Organizational Chart

The larger the project, the more critical the organizational structure becomes. In a small project, a single team member may be responsible for several functions, whereas in a large project the functions might require full-time attention. A very large project, for instance, often requires a deputy project manager.  A small project might have the senior technical staff member serving as a development manager. Definition of the project organization is a critical part of the planning process.

Project complexity also is a major factor when organizing a project. For example, a project that includes a large software development component typically includes a software development manager. This allows for a concentration of resources on a high risk area.  Unless a project is extremely small, it is useful to organize the project into functional teams. This approach leads to idea synergy and improved communications. The project manager is responsible for defining and selecting the team leaders. Team leaders can off-load some of the work of the project manager and take responsibility for completion of tasks. Team composition should be determined early in the planning phase, so that leaders are involved in the planning and also assist in defining a successful project plan.

Support Functions

While the project manager, in theory, is responsible for all of the management aspects of a project, rarely can all of these tasks be performed by one person. In fact, some should not be performed by the project manager due to the time consuming nature of the function. These necessary support tasks can be divided into administrative and technical support functions and are shown in the following figure.

- Project Management Support Functions

The administrative functions are fairly obvious and can be further expanded to include scheduling and budgeting in very large projects. Within the technical support functions, configuration management ensures that changes to the product being developed are controlled; quality assurance monitors and controls the quality of the product being developed; and testing verifies compliance of the product being developed to the stated requirements.

It is the project manager’s responsibility to organize the project support groups and to document their planned activities. In the basic project management plan, testing is considered part of the development life cycle to support a wide number of development methodologies currently in use by different state organizations.

Define Assumptions

Documenting the assumptions made in resource allocation is critical to the later success of the project. Without clear documentation of these assumptions, later changes in the staffing are very difficult and risky.

If, for example, a key person with a specialized technical skill was assumed in the plan, that assumption must be documented. Then, if that resource is unavailable to perform the task, the project manager can recognize the risk and make necessary decisions. Without documentation of the assumption, the plan is open to serious risk without the project manager realizing it.

Ongoing Reporting

Refer to Section 5, Project Execution, subsection Resource Loading Updates, for a discussion on how this information will be used during the Execution Phase of the project.

Identify Risks

A risk is any factor that may potentially interfere with successful completion of the project.  Risk management recognizes that a problem might occur.  When a problem develops, the risk of it happening is 100%.  By recognizing potential problems, the project manager can attempt to avoid a problem through proper actions.

Risks are inherently involved with scheduling resources. Sound resource planning makes allowances for dealing with risks in one or more of the following ways:

- The most recommended technique for risk allowance is to add an additional WBS task for risk management/risk reduction, and financial reserves can be set aside to deal with potentially delayed schedules.

- Add time to those tasks where resources are known to be a problem.  There is no rule of thumb for this multiplier; it depends on the degree of risk and the overall impact that resource problems can have on the project. The cost for this task would be derived from the Total Risk Hour from the Risk Analysis Worksheet.

- Add a percentage time multiplier to the schedule for specific individuals, particularly if new technology is being used or if the person providing the estimate is extremely optimistic. Remember that technical staff typically underestimate the time required to do any particular task.

- Where skill shortage is identified, add time and resources for training. By recognizing resource shortfalls and providing the necessary training, a project manager mitigates some level of risk.

Risk Management Process

The procedure that the team will use to manage project risks is defined in the planning stage, documented in the project plan, and then executed throughout the life of the project. Risk management deals with the following risk phases:

- Risk identification

- Risk analysis, quantification and prioritization

- Risk mitigation planning

- Risk response

The Risk Management Plan documents the procedures used to manage risk throughout the project. In addition to documenting the results of the risk identification and analysis phases, it must cover who is responsible for managing various areas of risk, how risks will be tracked throughout the life cycle, how contingency plans will be implemented, and how project resources will be allocated to handle risk.

Project risks are identified and carefully managed throughout the life of the project. It is particularly important in the planning stage to document risks and identify reserves that have been applied to the risks.

There are various areas that can affect a project, including:

- The technology used on the project

- The environment in which the project is executed

- Relationships between team members

- How well the project fits the culture of the enterprise

- How great a change will result from the project.

Risk identification consists of determining risks that are likely to affect the project and documenting the characteristics of those risks.  Don’t try to identify all possible risks that might affect the project, but focus on those likely to affect the project’s success.

Responsibility for Risk Identification

All members of the project team can identify risk, but the project manager has overall responsibility.  The project manager is responsible for tracking risks and for developing contingency plans.  Sometimes a risk identification “brainstorming” session can help in the initial identification process.  Such meetings help team members understand various perspectives and can help the team members better understand the “big picture.”

Risk identification begins in the early planning phase of the project. A Risk Management Worksheet (shown later in this section) is started during the planning phase. Then, as scheduling, budgeting, and resource planning occur, the worksheet is updated to reflect further risks identified in the planning stage.

At project startup, the Risk Management Worksheet is reviewed again, and any new risks are added to it. As the project progresses, members of the team identify new risk areas that are added to the Risk Management Worksheet. Also during the project, risks identified earlier may be removed.

Risks are documented so that contingency measures can be taken to mitigate their effects. Risks to both the internal and external aspects of the project should be tracked. Internal risks are those items the project team can directly control (e.g., staffing), and external risks are those events that happen outside the direct influence of the project team (e.g., legislative action).

Risk Management Worksheet Instructions

The risk categories/events shown on the Risk Management Worksheet are provided for guidance, and do not represent an exhaustive list of risks. The risk categories/events should be customized for each individual project.

The project manager, with the support of the project team, then evaluates each risk event for the following:

Loss Hours:

Indicate the expected increase in hours that will occur if the risk event occurs.

Probability:

Use the probability field to quantify the chance of the event taking place. Use a decimal value from 0 to 1 (e.g., .70).

Risk Hours:

This field represents the estimated risk for this event. The field is calculated by multiplying the loss and the probability fields.

Previous Risk Hours:

This field represents the value of risk hours reported in the previous period. A difference between this value and the current risk hours indicates a change in the risk status and is used to alert management that a change has occurred.

Preventative Measures and Contingency Measures:

The next two columns document the planned preventative and contingency measures that could minimize the effect of the risk event. The measures shown in the next figure are representative of common contingency measures, but are not an exhaustive list. The project manager should provide specific contingency plans for the specific project.

Responsible Person:

The individual assigned to track, report on or manage this specific risk.

Comments:

The comments column should be used to document items such as a change in value of risk hours from the previous period, management actions needed to contain risk, and status of preventive and contingency plans.

Total:

The sum total of values in column four is the total risk hours for the project and should be reported in the project plan.  This total should be multiplied by a blended rate for personnel and included in the WBS, Schedule and/or Project Estimate Summary Worksheet.

When does Risk Identification Occur?

Risk identification is a recurring event, it is not performed once and then set aside.  During the planning stage, risks and mitigation measures are identified and documented.  During the resource allocation, scheduling, and budgeting phases, associated reserve planning is also documented.

Risk identification, management, and resolution continues throughout the life of the project. New risks are developed as the project matures and external and internal situations change.  Old risks may go away or decrease in likelihood.

When probability of a risk increases, or when a risk becomes a reality and the project manager must deal with a real problem, replanning occurs. At this point, the project manager and project team develop strategies that assess the impact of the problem. This replanning may result in budget, schedule, or resource changes for completion of the project.

Contingency Planning

Contingency plans are developed as a result of a risk being identified. Contingency plans are pre-defined action plans that can be implemented if identified risks actually occur. If a problem actually occurs, the contingency plan must be implemented and reserves must be allocated.

As a guideline, contingency plans are developed for the top five risks associated with a project. For large projects the top five risks of each major sub-system may be actively tracked.  To properly implement a plan, a reserve is usually required where dollars and/or time are held by a project manager to apply to the execution of a contingency plan. Such contingency reserves are discussed in the appropriate sections of planning.  Without maintaining a reserve, the project manager is forced to go back for additional time or dollars for every risk as it becomes a problem. It is far more desirable to maintain a level of reserve where problems can be dealt with from within the original budget and schedule of the project.

There are some situations where nothing can realistically be done to prevent or deal with a risk. In this case, the project must be managed in such a way that the probability of the event occurring is minimized. If the event does occur, the project manager must replan the project and include the effect of the problem.

Risk Management Worksheet

A  description of all risks identified for the project, the probability of the risk occurring, the impact of the risk on the project, and the suggested mitigation activities.

Last Risk Assessment Date:						Prepared by:

| Ref # | Risk Category/ Event | Loss Hours | Probability | Risk Hours | Previous Risk Hours | Preventive Measures | Contingency Measures | Responsible Person | Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Personnel |  |  |  |  |  |  |  |  |
| 1 | Lack of knowledge in this hw/sw | 200 | .10 | 20 |  | 1, 2 |  | Development Manager |  |
| 2 | Insufficient resources available | 400 | .25 | 100 |  | 13 |  | Development Manager |  |
|  | Equipment |  |  |  |  |  |  |  |  |
| 3 | Delivery date slip | 100 | .25 | 25 |  |  | 3, 4 | Purchasing |  |
| 4 | Insufficient configuration | 100 | .15 | 15 |  | 5, 6 | 3, 4 | Technical Architect |  |
|  | Customer |  |  |  |  |  |  |  |  |
| 5 | Infighting | 150 | .2 | 30 |  | 7 | 8 | Project Manager |  |
| 6 | Unacceptable working environment | 200 | .3 | 60 |  | 9 | 8 | Project Sponsor |  |
|  | Customer |  |  |  |  |  |  |  |  |
| 7 | Third party involvement | 300 | .1 | 30 |  | 14, 15 |  | Steering Committee |  |
| 8 | Customer availability | 250 | .25 | 63 |  | 7, 16 | 29 | Project Sponsor |  |
|  | Logistics |  |  |  |  |  |  |  |  |
| 9 | Multiple customer sites | 300 | .2 | 60 |  | 20, 21, 22 |  |  |  |
| 10 | Physical separation of team and customer | 200 | .2 | 40 |  | 20, 21, 22, 23 |  | Project Sponsor |  |
|  | Organization |  |  |  |  |  |  |  |  |
| 11 | Team > 10 | 200 | .2 | 40 |  | 24, 25 |  | Project Manager |  |
| 12 | Customer people on team | 300 | .3 | 90 |  | 26 |  | Project Sponsor |  |
|  | Other |  |  |  |  |  |  |  |  |
|  | TOTAL RISK HOURS |  |  | 573 |  |  |  |  |  |

Risk Reserve	$22,920 at $40 average hourly cost

Suggested Preventive and Contingency Measures

- Provide appropriate training.

- Hire trained specialists.

- Install temporary hardware.

- Utilize internal hardware temporarily.

- Purchase additional equipment.

- Implement product functionality in a phased manner.

- Get agreement on who has decision authority; designate key user responsibility.

- Locate project team in our offices.

- Negotiate better environment.

- Ensure that all the resources are provided.

- Suggest/sell Functional Specifications before development.

- Unilaterally develop Functional Specifications.

- Adjust deadline and get our customer buy-in.

- Do not commit to third-party performance.

- Get third party commitment at least equal to (if not more than) our commitment.

- Get customer commitment to participate in the project.

- Increase estimates for the related tasks.

- Do not commit to response time unless absolutely necessary and, then only if a study is done by knowledgeable persons.

- Establish access to product support personnel.

- Hold regular meetings with customer.

- Maintain constant written and oral communication with remote personnel.

- Visit remote sites as needed.

- Demonstrate incremental results.

- Divide staff into teams and assign team leaders.

- Dedicate our management resources.

- Establish final authority of our project manager.

- Use proven hardware for development if possible.

- Reduce functionality to meet deadline.

- Document our assumptions and understandings and get Customer’s sign-off before investing substantial resources.

- Design an alternate (contingent) solution strategy.

Risk Identification Summary

(Top Five Risk)

The Project Plan Template

The project plan forms the basis for all management efforts associated with the project.  The information contained in this plan is required for IT projects in varying degrees.  The exact format of the information may vary from the template presented here, however, the basic information is required as defined.

This plan template emphasizes documenting only the pertinent information associated with the plan. The blank template for the project plan is provided in Appendix B: Forms.  The forms are actually WordTM documents which are available for download from the KITO website.

The plan does not require verbose textual content filled with boilerplate material. Information associated with detailed procedures for executing such processes as technical development, configuration management, and quality assurance should be documented in the state organization’s procedures. For example, the configuration management information contained in the plan might reference a procedures document that defines the specific activities and responsibility for each configuration item.  The project plan may only summarizes who is responsible for the configuration management activities, what is under configuration control, and where the repository will reside.

Plan Approval

It is important that project plans are approved prior to beginning a project. These approvals should be easily located at the beginning of the plan to emphasize support for the project plan. In the template format, approval signatures are included on the cover of the plan, as shown below.

- Project Management Plan Approval Signatures Form

Project Summary

The above signatures represent agreement with the attached plan including agreement with the activities, the risks, the effort and the cost of the associated project.

Following the approvals page, there should be a project summary and charter information that defines:

- The project goals, objectives and success factors.

- The estimated value of the project.

- The duration of the effort.

- The purpose of the project.

- Major dependencies/constraints.

The Project Summary is maintained over the course of the project. The first page includes areas that need to be filled in and then updated with each new release of the plan. These include:

- Project name and start date.

- State organization, name, and submitted by.

- Prime Contractor (if applicable) and date awarded.

- Current stage of the project.

- Project status in terms of schedule and budget.

- Budget summary.

Page 2 of the Project Summary includes points of contact and prime contractor information.

The following two pages show a completed sample project summary from the template.

1. Project Summary (Sample)

Information in the project summary areas was started during the project concept phase and should be included here

- Project Summary - Continued

- Points of Contact

- This should be the list of individuals that will be involved with the project during the execution phase.

Project Charter

The project charter follows the project summary information. Like the project summary, the project charter information was developed during the project concept phase and finalized in the planning phase.  It includes a business problem, statement of  work, objectives, success factors, project dependencies, and constraints.  A sample of the completed information is shown below.

2. Project Charter(Sample)

- Business Problem.

- All projects start with a business problem/issue to solve.

- Sample

The lack of a statewide automated planning system for scheduling transportation road repair maintenance resources has resulted in road closures, duplicated capital expenditures, and increased staff overtime costs.

- Statement of Work (Goal).

The statement should be short and to the point. It should not contain language or terminology that might not be understood.

- Sample

Design and prototype an automated, dynamic planning system by Q4, 1997, based on an SQL database and GUI front end. Based on the prototype, pilot the system  and complete full implementation by Q4, 1998.

- Project Objectives:

Provide a brief, concise list of what the project is to accomplish.

The project objectives are a detailed version of the statement of work. Taken with  the statement of work, the objectives define the boundaries (scope) of the project.  The objective statement can also be seen as a decomposition of the statement of work into a set of necessary and sufficient objective statements, including:

Outcome - Be specific in targeting an objective

Measurement- Establish a measurable indicator(s) of the progress

Ownership - Make the object assignable to a person for completion

Timeframe - State what can realistically be done with available resources

- Sample

1.	Define the planning requirements for the system by Q2, 1997

2.	Define user needs in terms of inputs and outputs by Q2, 1997

3.	Conduct user and stakeholder meetings during Q1 and Q2, 1997

4.	Develop the prototype and test, with a completion date of  Q4, 1997

5.	Conduct the pilot of system with completion by  Q2, 1998, with the pilot lasting at least three months

6.	Complete system acceptance and user documentation by Q3, 1998

7.	Complete system installation at all locations by Q4, 1998

- Success Factors:

List factors that will be used to determine the success of the project.

Short-Term

1.  Complete System acceptance by Q3, 1998

2.  Have system installed in 7 locations by Q4, 1998

3.  Have all locations,  including contractors installed and trained by Q1, 1999

Long-Term

1.  Reduce total maintenance project cost by 3% per year in the 12 months following implementation.

2.  Reduce total maintenance project cost by 5% per year in the subsequent following 12 months.

- Project Dependencies/Constraints:

The schedule for implementation for such a large, complex system is very constrained.

Project Trade Off Matrix and Status Summary

Managing a project requires the balancing of three factors: resource, schedule, and scope.  These three factors are interrelated, i.e., a change in one of them causes the others to change as well.  The project trade off matrix shows the relative importance of each factor:

- constrained means the factor cannot be changed

- accepted means the factor is somewhat flexible to the project circumstance

- improved means that the factor can be adjusted.

Also included on this page of the template is a matrix for project status. The matrix  reflects whether the technical, schedule, and cost estimates for each task are behind, on schedule, or ahead of schedule. Comments are added for any deviation from the original estimate.  For each project, the unique teams or phase should be filled in the appropriate category.

3. Project Tradeoff Matrix and Status Summary

Project Organization

The project plan should include a description of the project organization team.  A project manager is required for every project.

Many plans may also include a narrative of key project member responsibilities. This would include the person’s name, project position, and key responsibilities.

Small projects will require less organizational definition than larger projects, but responsibilities should always be defined.

See Resources Planning for a sample Project Organization Chart.

Activity List

Activity sequencing involves dividing the project into smaller, more manageable components (activities) and then specifying the order of completion.

Activity List (Sample)

Work Breakdown Structure

Work Breakdown Structure

The activity list can also be graphically presented as a WBS and included in the project plan. The WBS, describes each task required in the project. For large projects, a description showing how specific tasks are to be completed by specific project teams may also be included.

Tasks are assigned as work packages which define schedules, identify requirements to be completed and describe specific work to be performed. Refer to Activity Definition and Sequencing for further information on development of a work breakdown structure.

Work Product Identification

The list of project deliverables that includes the date due and the person responsible for the delivery should be part of the plan.  This information is derived from the project activity list, and is expanded to include the assignment of the deliverable to a specific author and tracking of delivery of the document. See Activity Definition and Sequencing for a sample of a Work Product Identification Form.

Project Schedule

The project schedule included in the project plan can either be a GANTT or PERT chart.  It should include milestones, task dependencies, task duration, work product delivery dates, quality milestones (reviews/audits/inspections), configuration management milestones, and action items (with deadlines and responsibilities). See Overview of Project Scheduling for samples of GANTT and PERT Charts.

Estimated Cost at Completion

This estimated cost at completion is an assessment of the total project effort in terms of either time or dollars.  See Budgeting within this section for a sample of the Estimated Cost at Completion Worksheet.

Resource Loading Profiles

The staffing plan shows the number of personnel, by type, that are required on the project on a monthly basis.  This information is compared monthly on a planned versus actual basis.  See Resource Planning for a sample Project Staffing Plan.

Project Requirements

The detailed listing of project requirements, if appropriate should be included. Refer to Requirements Definition for a sample.

Risk Management Plan

A Risk Management Plan for the project is included. A risk is anything that could potentially affect the successful completion of the project.  The contractual, management, and technical risks associated are identified and assessed for the probability of the risk occurring, the cost to correct if the risk occurs, the impact of the risk on the project, and the suggested mitigation activities.  Refer to Risk Identification section for further information and sample forms.

Configuration Management Plan

The Configuration Management Plan defines the person responsible for project configuration management, the procedures used, the planned configuration items, planned release dates for configuration items, and resources required to conduct Configuration Management.  This Configuration Management Plan is summarized in a format depicted in the figure below. Refer to the Configuration Management section for further information on configuration management planning.

- 12. Configuration Management Plan

Quality Plan

The Quality Plan defines the person responsible for project quality activities, the procedures used, the planned quality activities, and resources required to conduct QA activities is summarized in the project plan.  Refer to the Quality Plan Development section for further information on quality planning. The QA Plan is summarized in a format illustrated in the figure below.

- 13. Quality Plan

Top Five Issues

This form identifies the Top Five Issues  that have been identified for this project.  It defines the person responsible for resolving the issue, and an associated open and close date, with proposed or recommended solutions.

- 14. Top Five Issues

| Issue Description | Responsible Individual | Open Date | Closure Date | Status |
| --- | --- | --- | --- | --- |
| Change order pending for AP processing | A. Smith | 4/5/96 |  | Estimated release date 4/15/96 |
| Enhancement number 1 inactive; requirements still not defined | D. Hall | 4/1/96 |  | Awaiting input form Jim who needs to meet with Bob on 3/15/96 |
| Out of scope item on month end processing must be decided | A. Smith | 2/15/96 | 3/1/96 | Determined effort was out of scope. No action to be taken. |
| Configuration Item Status Reporting system not yet installed. | B. Jones | 1/15/96 | 1/25/96 | System installed and operational. Baselines entered into CM. |

Issue Item Status

The plan should include a list of issues that are maintained as part of project tracking.  A sample table is shown here.

15. Issue Status

Action Item Status

A similar chart as the one above can be used to show Action Items that need to be tracked at the beginning and throughout the project .

SECTION 3

PROJECT MANAGEMENT PLANNING

INTRODUCTION	1

Planning is the Seed for Success	2

Responsibilities	2

Terminology	2

What is Project Planning?	4

The Planning Process	4

Importance of the Project Plan	6

Steps in the Planning Process	6

Develop Project Tasks	7

Define Project Tasks	9

Define Project Development Phases	10

Define Task Relationships	12

Defining Deliverables	12

Overview of Project Budgeting	13

Identify Cost Factors	13

Project Estimate Summary Worksheet	14

Instructions	14

Review the Cost Estimates	19

Estimated Cost at Completion Report	19

Configuration Management	21

Configuration Management Organization	21

Configuration Management Plan	22

Tasks During the Planning Phase	23

Relationship to Quality Management	23

Authority and Responsibility	24

Configuration Elements	24

Configuration Management Procedures	24

Configuration Management Process Flow	25

Storage of Control Items	26

Configuration Management Goes Beyond Development	26

Overview of Project Scheduling	27

Define the Type of Schedule	28

Define Precise and Measurable Milestones	30

Estimate Task Duration	30

Define Priorities	31

Define the Critical Path	31

Document Task Relationship	31

Document Assumptions	32

Review the Results	32

Scheduling Tools	32

References	32

Quality Process	33

Creating the Quality Plan	34

Responsibility for Quality	34

Independence of the Quality Assurance Team	34

Checklist	35

References	35

Importance of Project Requirements	36

When are Requirements Defined?	36

Requirements Specifications	36

Who Defines Requirements?	37

Requirements Traceability	37

Approvals	39

Managing Requirements Changes	39

References	39

Overview of Resource Planning	40

Determining the Size of the Team	40

Determining Required Skills	40

Identifying Required Non-Labor Assets	41

Define Resource Profiles	41

Forming the Team	42

Support Functions	44

Define Assumptions	45

Ongoing Reporting	45

Identify Risks	46

Risk Management Process	46

Responsibility for Risk Identification	47

Risk Management Worksheet Instructions	48

When does Risk Identification Occur?	49

Contingency Planning	49

Suggested Preventive and Contingency Measures	52

The Project Plan Template	54

Plan Approval	55

Project Summary	55

Project Charter	59

2. Project Charter(Sample)	59

Project Trade Off Matrix and Status Summary	61

3. Project Tradeoff Matrix and Status Summary	61

Project Organization	62

Activity List	62

Work Breakdown Structure	63

Work Product Identification	63

Project Schedule	63

Estimated Cost at Completion	63

Resource Loading Profiles	63

Project Requirements	63

Risk Management Plan	64

Configuration Management Plan	64

Quality Plan	65

Top Five Issues	66

Issue Item Status	66

Action Item Status	66