Copyright © 1999-2008 State of Kansas.  All rights reserved.

Project

Management

Methodology

CLOSE-OUT

EXECUTION

STARTUP

PLANNING

CONCEPT

Project Management Methodology

Release: 2.3

FSR Release: 2.4

Permission to view, use, and copy this material for personal

use is hereby granted, provided:  1)  The document is used

for informational purposes only.  2) The document is used

for non-commercial purposes only.  3) The document

includes the above copyright notice and this permission

notice appears in all copies.

What Happens During Project Execution?

Once a project reaches the execution phase, a project team and the necessary resources should be in place to perform the project tasks.  The project plan should have been developed and baselined.

The project team shifts its focus from discovery to participating, observing, and analyzing what is being done.  This process is graphically presented below.

- Management During Project Execution

The critical elements for the project management team are:

- Track and monitor project activities to measure actual performance to planned performance

- Review and communicate status and future actions

- Monitor and mitigate potential risks

- Execute a change management process to control changes to the project’s objectives, specifications and overall definition

- Execute an issue tracking process to ensure that there is a central repository for project issues that are addressed in a timely fashion

- Have in place a corrective action process to document and track plans to correct an issue that impacts the plan and which establishes guidelines for re-planning.

Project Control Process

The project plan serves as the basis for the project's monitoring, controlling, and reporting activities.  By following the plan and gathering relevant data for the status meetings and reports, information will be available to accurately identify issues and problems, minimize project risks, and monitor, control, and report progress.

Once a project has been baselined and the project starts, then it needs to be directed.  This next series of documents deals with the “control” of the project after it has begun.  This involves processes that need to be in place to ensure that the project progresses according to plan. During tracking, monitoring, and reviewing, the project team collects data to assess the current state of the project.  These activities always include:

- Review the completed activities

- Identify milestones reached

- Identify problems or issues

- Update project schedule and progress information

- Update budget and variances.

Project controls which may be needed include:

- Addressing issues

- Reviewing change requests and making recommendations

- Preparing action plans

- Rescheduling

- Reallocating resources

- Adding resources and/or equipment.

The next figure presents a graphic view of the project control process.

Project Control Process

Preventing Problems is Better than Fixing Them

Projects fail due to inattention to basic control principles.  Too many times the project team is busy getting on with “completing the project” and not spending the time and energy anticipating problems.  Then, once a problem is suspected, the team acts too slowly to resolve the root of the problem.

Preventing problems is far easier and less costly than solving them and the best way to locate a problem is to always be looking for it. For example, frequent and unchecked changes to the requirements specifications are a known leading source for design problems.  Listed below are some major control issues:

- Poor time and cost estimates

- Frequent and uncontrolled changes to the baselined requirements

- Difficulties in concluding the project because of lack of completion criteria

- Frequent replacement of development personnel

- Inadequate tracking and directing of project activities.

Once a project has started, one of the most common problems is that the project manager, and possibly the full project team, is unaware of the existence of a major problem at a stage when it could be contained and corrected.  This can be improved by the consistent sharing of information and taking action based on that information.

The tracking, monitoring, and reviewing processes apply in varying degrees to all projects.  As in all the sections of this document, caution should be taken not to use the processes as a “recipe,” but to analyze the specific project and develop management structures that best meet the needs of the project.

What is the Approval Process?

Project Quality management ensures that there is adequate review of project deliverables at phase completion.  Approval is a formalized process ensuring that the appropriate levels of testing and review have been completed.

The process of ensuring that appropriate approvals are obtained is part of the management function and is not strictly a technical function.

The approval process ensures that each project phase and associated deliverables are successfully completed before beginning subsequent phases.  Management gets a comprehensive view of the current project status.  Information necessary to ensure that deliverables satisfy the specific business needs of the state organization is also received.  Project approval also allows management to reassess the direction of the project, as necessary, and to provide project planning updates, as required.

There are typically three types of approval processes.  Approvals discussed in this section occur during the execution stage and include:

- Project Plan and Plan Changes, at the beginning and after changes to the baseline

- Phase Reviews, at the end of each phase

- Deliverable Reviews, as they are completed and at the end of the project.

The later two approval processes are shown in the figures following this page.

Contractor Payments

The approval process normally triggers contractor payments.  As a general rule, Kansas IT projects are designed for payment to contractors based on prearranged and negotiated deliverables.  The overall contract should be capped.  The cap is a dollar amount not to be exceeded for the overall project.

In the case of custom system development projects, the state should avoid making payments solely on the basis of client testing.  Thus, a portion of the project budget should be reserved for payments based on integration testing of subsystems as well as full integration testing of the entire system.  It is important that contractors receive a revenue stream as the project goes along.  However, the revenue stream should be designed in such a way that final payments are not made until after integration testing and deliverables are completed and signed off by the project manager and key users.

- Sample Phase Approval Process

- Sample Deliverables Approval Process

The approval process takes place on two levels.  First, the technical teams agree that a phase has been completed, and then a phase completion meeting is held to formalize the event and move on to the next phase.

Documentation approval can also be formalized, but on a more limited scale, possibly among sub-sets of the project team.

For document approval, the project plan should contain a more detailed deliverable list that includes not only date items and WBS relationship, but also the name of the person(s) who must approve the document. The figure below provides a sample of how one project summarized this information.

### Suggested Approval Points within Project Execution

| #### Document Name | To Be Approved by |
| --- | --- |
| Project Plan Hardware Procurement & Install Plan Site Prep. and Facilities Plan Network Plan Test Plans Quality Plan Data Plan Training Plan Contingency Plan Pilot Implementation Plan Roll out and Cutover Plan Maintenance Plan Support Service Plan Turnover Plan Warranty Plan Backup and Recovery Plan Gap Analysis Report Implementation Recommendation Report Re-engineered Process flows Detailed Requirements Detailed Design Interface Design Document Training Curriculum Certifications | Steering Committee Steering Comm./Imp. Team Steering Comm./Imp. Team Steering Comm./Imp. Team Imp team/stakeholders Steering Comm./Imp. Team Imp. Team/stakeholders Imp. Team/stakeholders Imp. Team/stakeholders Steering Committee/Imp team/stakeholders Implementation Team Steering Comm./Imp. Team Steering Comm./Imp. Team Steering Committee Implementation Team Steering Comm./stakeholders Steering Committee Imp. Team Stakeholders/Exec Mgmt Imp. Team/stakeholders Imp. Team/stakeholders Implementation Team Imp. Team/stakeholders Imp. Team/stakeholders/Steering Committee |

What Happens During Project Execution?

There are two processes that will significantly increase the chances of project success and will help with the overall management of the project.  These are:

- Change Management

- Issue  Management

During project planning, the management approach for both of these areas is identified.  At the time of project plan baseline, responsibility for these areas should be assigned.  At the start of project Execution, both of these processes should be in place and working.  In many regards, the processes are similar and the purposes are the same -- to help achieve control of the project. At times, a requester may not be sure if an item is a change or an issue.  In fact, there are times when an item will start in the issue process and end up in the change process.

The difference between an issue and a change rests in how a project is impacted.  Change, as indicated in its name, affects the view of the project and will impact the scope, project definition, and/or specification.

Issues may not have an impact on the defined project’s product -- scope, definition, or specification.  Issues are identified in the form of questions, problems, or suggestions raised by the project team, management, or contractor.  They can often affect the status of tasks or deliverables, which would result in changes to cost and schedule.

You Can't Manage What You Don't Control

As discussed earlier, too much change in a project is one of the major reasons projects fail.  This is the area in which project managers/teams continually lose control.  The reason is a lack of discipline within the project team and with the customer to resist “changing” the stated product of the project.  A solution is to establish a critical baseline of the project’s products and to document it.  These documents are the project plan, the product specification, and other development documents that are placed under Configuration Management.  Whenever a question is raised, the baseline documents are always the reference point.  Anything that alters the baseline is a change.

If an individual is not sure if it is a change, then treat it as an issue.

Part of controlling a project is to have established change and management processes that are unique to the project. These processes are established as part of the project plan and kept current until the project close-out.

The key elements to these processes are:

- A central repository for change information and for issue information

- Summary of information for the processes on either a change request form or issue form (as shown and discussed later in this section).

- Configuration Management processes

- Assignment of a Change Manager and Change Control Board (CCB).

- The manager should be either the project manager or a member of the status tracking/review team.  If the project manger is not the Change Manager, then he/she is at least a member of the Change Control Board.

- The Change Control Board should consist of the Change Manager, key technical and management staff from the project team, representation from executive management, stakeholders, and user communities.  The size of the Board should be kept to a working group of not more than 10-12 individuals.

- Assignment of an Issue Manager. Typically this is someone in the administrative project area who will work with the Project Manager and can prepare the material for the project status meetings.  In a small project, it may be the project manager.

- Inclusion of change and issue summary information as part of the standard project status meetings.

- Consistent and ongoing evaluation of change and issue items and development of appropriate resolution/implementation strategies.

What is Change Management?

Change Management is a process that provides a mechanism to identify and handle change.  It is a part of Configuration Management.  Change can affect the scope, cost, quality, and nature of the contract deliverables, as well as the functioning of the project team.

In order to maintain the balance between requirements and the schedule, the project team should use a Change Management Process.  This process allows for change during the project's life cycle but always puts the change in the context of the latest documented agreement (project plan) between the team and management.

The Change Management Process consists of a series of steps that allows changes to be identified, evaluated, priced, and tracked through closure.  If the change is significant, you should perform a Cost Schedule Impact Analysis (CSIA).  This analysis is performed under the direction of the Project Change Manager and approved by the Change Control Board (CCB) and the Executive Oversight Committee or Steering Committee.

A sample of a Change Control Process is shown on the following page.  This process may be too complex for some projects and not complex enough for others.  The goal is for projects to implement and use a process that fits the project.

- Change Control Process

The Change Control Form

Stakeholders should submit information on any change to be considered.

The Change Control form shown in this framework can be used and is included in Appendix B: Forms.  A project team can add or change the form as required.

The form is additive. In other words, additional information is completed on the form as it moves through the process.  This process is iterative in that it will keep occurring until the project is complete.

Phase 1 - Requester Information

The Change Request form is found in Appendix B: Forms, includes the following:

Identification Block - Is completed by the requester and identifies the change request title, which will be used in subsequent communication, the date submitted, and the person and organization submitting the request.

Proposed Change Description and References - Describes the change being proposed and clearly identifies whether the change is system, organizational, or procedural in nature.  Any reference material that will assist the reviewers should be identified and attached.

Justification - A discussion of why the change is being proposed, including a cost benefit analysis. In other words, how will the customer and state organization benefit from the change?

Impact Statement - If the change is not implemented, how will it adversely affect the customer and state organization?

Alternatives - List at least one alternative (more if possible) to the change you are proposing, and indicate why the proposed change is better.  Briefly indicate why the alternative is not the better choice.

Attach any supporting documentation that helps to clarify the proposed change.

When complete, submit to the Project Change Manager.  At that time, a control number will be assigned so that the change request can be tracked to completion.

Phase 2 - Initial Review of the Change Request

All change requests will be reviewed on a regular basis by the project Change Control Board.  This Board will typically meet on a weekly, bi-weekly, or monthly basis. The actual schedule will depend on where the project team is in terms of the project life cycle.  During phases that typically have a high volume of change, the Board might meet weekly.  During other phases, the Board might meet once a month.  The Change Manager will drive the schedule based on the number and complexity of change requests.

As part of Phase 2 of the Change Control Process, the Board will complete the second part of the form which includes:

Initial review results and disposition - The Change Control Board will review the initial request and determine whether to proceed, reject, or defer the request.  In moving forward, the request may be assigned to an analyst for an initial impact analysis.

Phase 3: Initial Impact Analysis

The assigned analyst will make an initial assessment of the cost, schedule, and resources needed to implement the proposed change. If the requested change is complex, and an initial assessment cannot be made quickly, a Cost/Schedule Impact Analysis (CSIA) should be requested.

The analyst will indicate this and will estimate the cost, schedule, and resources needed to perform the CSIA.

The Change Control Board will once again review the requested change and either accept, reject, or defer the change.

Phase 4: Final Review Results and Change Priority

When the analysis has been completed by the assigned analyst, and the cost, schedule, and resource needs are identified, the management team will submit the change to executive management and/or Steering Committee for review.

After their approval, the appropriate processes will be followed to update contracts and the baseline documents.

- What is Issue Management?

Issue management is a process that provides a mechanism to process and review issues.  Issues that develop during the project need a way to be raised by the project team and for the team to know that they will be addressed.

When issues arise, they need to be resolved in a consistent and disciplined manner in order to maintain the quality of the deliverable, as well as to control schedules and cost.  The Issue Resolution Process ensures that the differences, questions, and unplanned requests are defined properly, escalated for management attention, and resolved quickly and efficiently.

The Issue Management Process should handle technical problems or issues, as well as process, organizational, and operational issues.  The process considers:

- Appropriate procedures for issue escalation

- Level of management that needs to be involved for escalation

- Required time for resolution

- Responsibility for researching or resolving the issue

Defined below is a process for submitting, reviewing, and gaining closure on an issue within a project. This is a process that may be too complex for some projects and not complex enough for others.  The goal is for projects to implement and use a process that fits the project.

- Issue Control Process

The Issue Resolution Form

The Issue Resolution Form gives everyone involved with the project a way to report issues or problems.  It provides a template for documenting the issue, assessing the impact of the issue, making recommendations, determining the cost (people and assets), and time required to resolve the issue, if it becomes a change.

This process is also iterative in that it will keep occurring until the project is complete.

Phase 1 - Requester Information

The Issue Resolution Form is included in Appendix B: Forms.

The Issue Resolution Form is divided into major categories.  The first part is completed by the person reporting the issue.  Its major categories include:

Identification block -  Identifies the issue title, which will be used in subsequent communication, the date submitted, and the person and organization submitting the issue.

Issue classification and description -

- Description

- Recommendations

- Impact (if not resolved)

- Date Required and Proposed Assignee

Each category should be self-explanatory, but individuals should be directed to the issue manager for assistance as needed.  Attach any supporting documentation that helps clarify the problem or issue, such as report outputs, user screens being used, steps performed leading to the problem, error messages, etc.  When complete, submit to the Issue Manager.  At that time, a control number will be assigned so that the issue can be tracked to completion.

Phase 2 - Initial Review of the Issue

All issues will be reviewed on a regular basis by the project status group at the project status meetings.

As part of Phase 2 of the Issue Resolution Process, the group will complete the second part of the form which includes:

- Reviewer information and initial comments

- Estimate of additional effort (CSIA prepared if further evaluation required), if appropriate

- If the issue becomes a change, responsible person and planned completion date

- Project Manager signature

- Phase 3: Tracking

All action items will be tracked until they are resolved.  The Issue Manager will report on all open issues at the status meetings.  If the list of issues is too long, only the new issues will be discussed.  At times, it may be advisable to pre-distribute issue information so that the group can review the material before the meeting.

Phase 4: Final Review Results and Change Priority

When the issue or problem has been resolved and verified, the actual date the problem was resolved and an approval signature completes the issue resolution process, and the issue is closed.

Some issues may need executive management and/Steering Committee approval. The appropriate processes should be followed to update contracts and baseline documents.  If the issue does become a change, the configuration management process could be to transfer the change to the change control process and track it as a change.

The Best of Plans can go Wrong

When a project encounters problems, the actual problem needs to be sized and decisions made on corrective actions.

If the project is off track or over budget, steps should be taken to determine the following:

- Is the project still meeting its original objectives?

- Are the issues so great that the project must be replanned?

- Will the project meet the organization’s business needs?

The corrective action process can go hand-in-hand with the change control process; however, the change control process is not intended to solve problems that need to be addressed in an urgent manner or where there is a question on the soundness of the project.

Generally, problems that fall into the category of needing corrective action require quick action by the Steering Committee.

Where Problems Come From

Situations that normally require corrective actions fall into the following categories:

- Internal

- A particular task is behind schedule or over budget and it impacts the overall project plan

- A particular task was missed, with no work around, and it was on the critical path

- A major milestone is missed

- The functionality of the project does not meet objectives.

- External

- A major technical problem with the selected technology may have surfaced, and the resolution to the problem does not allow the project to be developed as specified.

- The state organization environment has changed, and the current IT project is not part of the solution for meeting their business needs.

All four of the internal situations identified above represent increasing severity for the project team and span a wide range of decision making processes, from simple additional attention at the status meeting to developing complete and detailed corrective plans, to stopping work orders.  Each of these situations means that the project is falling further behind schedule and over budget.

A key part of project management is providing quick action to identified problems and developing successful corrective plans.  Corrective action plans can take the form of replanning, reallocating resources, or changing the way the project is managed and organized.

The corrective actions available to the project manager center on cost, schedule, and technical performance parameters of the project. However, stakeholders and executive managers should also be involved at an early point in the process. They, too, have the ability to impact the corrective action process by shifting business priorities, reaffirming their support for the project, and showing commitment to having it replanned.  If they are not brought in early, that support becomes harder to obtain.

- Fix the Problem

An effective control process doesn’t just track, monitor, and review, but also re-directs the project if a major problem occurs. The first rule is to try and protect the overall integrity of the project schedule.

Recovery Plan

The goals of the recovery plan are to:

- Fix the problem quickly

- Limit the damage.

Detailed recovery plans should be put in place if a problem could cause harm to some aspect of the project.  The plan should:

- Identify the owner of the recovery plan

- Identify the sequence of activities that must occur to complete the resolution

- Determine the dates when each activity of the plan will be started and completed, and identify the dependencies of each activity

- Ensure that the appropriate people approve the plan

- Reflect the outcome, if the recovery plan is successful, in terms of schedule, activities modification, and cost.

All recovery plans are tracked following the exception reporting requirement covered in the Tracking and Monitoring Project Performance section of this manual.

- Review Process

Just as tracking and monitoring are critical to controlling a project, so too is reviewing.  One of the major causes of a project getting off track is the lack of attention to:

- Formal and consistent project reviews

- Setting up and using informal assessment methods.

The focus of project reviews is to ensure that information is being shared and communicated. Where tracking and monitoring focused on the process of measuring actual project performance to the baseline, reviewing focuses on sharing that data and other related information with the project team and stakeholders throughout the project.

As in all other areas of project management, the review process needs to be tailored to the specific project. There is no formula for defining the type and frequency of project reviews. However, there are some minimum activities that should be performed, such as:

- Status meetings should be held and attended by project team members responsible for key project organization and deliverables.

- Executive Reviews - as needed.

- Team meetings - as needed.

- Independent Reviews - as needed; will depend on the size of the project and the risk. However, each organization is encouraged to develop its own schedules and standards for quality reviews. Details on the actual independent reviews are provided in ITEC Project Oversight Policy #2510.  A copy of this policy appears in Appendix E, ITEC Policies.

- Technical Reviews  - are driven by the life cycle being used and the particular stage of the project. For example, during system design, the reviews are concerned with the stage of the design and detailed design reviews, possible design walkthroughs, and peer reviews.

Informal Review Process

The informal reviews are the processes that the project manager and key project staff set up to measure the “atmosphere” of the project.

This information can be gathered by:

- Walking the halls

- Visiting team work areas

- Sitting in on some team status meetings

- Inviting a key developer for coffee

The purpose is to get input from all parties on issues beyond what is presented in the formal reviews.  Having a set, consistent format limits the open exchange of information. For example, by talking with one team member, it might be discovered that a key technical staff member is very unhappy about some decisions on the project.  This unhappiness has not really been formulated; it may be only a “hunch,” and no one is interested in “hunches.” This unhappiness might escalate to the point where a person would leave the project, and/or it could develop into a major problem.

Part of the project manager’s strategy includes collecting information and interjecting it into the formal processes, where it can then be analyzed to determine if actions are required.

Lastly, the way a project is organized will drive the way the project is reviewed.  Each key project activity needs to be tracked and reviewed as such, and the person or group responsible for the activities will need to provide input to the control process.

- The Status Review

The cornerstone of the project review process is the project status meeting.  The emphasis of the status meeting is consistency and structure. The project team should know that this meeting is not optional.  For this reason, it is recommended that status meetings occur regularly and consistently throughout the project life cycle.  Meeting too often is disruptive and does not allow the project team to focus on other tasks.  Not meeting enough will allow issues to go unresolved.

Some projects set up the project status meeting on the same day, at the same time, and at the same place. Another hint is that the meeting time should be on Tuesday, Wednesday or Thursday to avoid Mondays and Fridays, since these days are frequently taken off and generally produce rescheduling issues.

This way, participants can set their schedule and the schedule forces a routine to be established. Consistent meetings also drive a discipline into the project organization.

Team Meetings

The first team meeting serves as a training session for the participants.  The training session covers how future meetings will be conducted and what each participant’s roles and responsibilities will be during and after the meeting. Each member should have at least one or two backups who should attend the first meeting.

Preparation for this meeting is critical and should map to the status report generation that will be discussed in the Tracking and Monitoring Project Activity section.

The following topics should be covered in the first meeting:

- How are risks to be managed and reported on?

- How will changes and issues be tracked and reviewed?

- Who will keep the schedule and cost information, and how will it be updated for review?

- What are key lessons learned from other projects?

- Which is the baseline plan?

Attendees should be specifically selected and the numbers limited. They should consist of individuals who can provide status information and contribute to issues, risks, and general status discussions.

As a guideline, if the project team is small, then the full project team may attend.  If the project team numbers 10 to 24, then only lead team members (planning, development, test, quality, etc.) should attend.  For projects larger than 25 members, attendees should be the team leaders.

The bottom line is that the persons attending the meeting communicate the status of the project activities and action items for their assigned area of responsibility. However, the number of attendees should be controlled so that the group is not too large to be productive.

A location should be selected that will provide the fewest disruptions. It should not be in someone’s office, or in a public area. A private conference room where telephones can be controlled is a good location.

Disruptions cause the meeting to appear disorganized and cause the length to extend.  This results in people not wanting to attend because it is viewed as a waste of time.

An agenda that is set with given timeframes is important.  A sample agendas is provided on the next page.

- Status Meeting Agenda

Project X

| Meeting Date: April 10, 1995 (Tuesday) |  | Meeting Time: 2:00 pm to 4:30 pm Total Time 2.5 Hours |
| --- | --- | --- |
| Meeting Location: Main Conference Room |  | Attachments: None |
| Leader: L. White (Project Manager) Bud Smith (Alternative) |  | Note Taker: R. Green Laurie Davis (as needed) |
| Attendees: C. Cooke L. White B. Davison R. Wise M. Strawn | R. Chapman T. Elsmore R. Tom J. Bicknas G. Kennon | Please Bring or Prepare: - All outstanding project issues and change requests - Any written documentation pertaining to activity deviations or new risk elements. - Standard project status report and attachments. |

| Agenda Item | To Be Accomplished | Person Responsible | Time Allotted |
| --- | --- | --- | --- |
| Project overview for reporting period | Inform & Discuss | L. White | 15 Min. |
| Schedule overview | Inform & Discuss | T. Elsmore | 15 Min. |
| Financial overview | Inform & Discuss | J. Bicknas | 10 Min. |
| Technical overview | Inform & Discuss | G. Kennon | 10 Min. |
| X team for project | Inform & Discuss | R. Tom | 10 Min. |
| X team for project | Inform & Discuss | C. Cooke | 10 Min. |
| Change Management update | Update | T. Elsmore | 20 Min. |
| Issue list review | Update | J. Bicknas | 20 Min. |
| Risk Management update | Update | G. Kennon | 20 Min. |
| Other issue | As defined by presenter | L. White | 20 Min. |
| Review of action items | Review | R. Green | 5 minutes |
| Close Meeting | Review | L. White | 5 minutes |

Purpose of Meeting

The purpose of the Project Status Meeting is to coordinate the schedule, resource, and financial needs of the project.  The objective will be to share and receive data, and to make group decisions critical to the project plan. Areas of prime interest are the financial, schedule, and technical issues of each group and how they work together within the overall project structure.

Process for Meeting

It is expected that each person will be prepared to update their status report from the previous reporting period and to discuss key issues and topics. Key areas are: costs, schedules, current and next period activities, issues, and change elements, and other topics that require discussion.

Ground Rules for Status Meetings

Since a large percentage of project time is spent in meetings of one form or another, a set of rules should be applied to each meeting type.  These rules follow standard meeting management principles:

- Start and end on time

- Come prepared

- Bring handouts; information should not just be in the attendee's head.

- Summarize information; do not read it.

- A list of action items and the status reports should be the by-products from the meeting. The action items and discussion topics should be written up and disseminated. If a project action item, change issue, or new risk element is mentioned, then the support person responsible for distributing the status meeting information should ensure that the responsible project team member is informed.

Since a project manager is responsible for reporting on the project’s status to other levels of the organization, written materials are needed to complete the necessary reports.

If an activity is not on the schedule, then the status meeting member should address:

- Why task completion is late or early

- What other areas are/might become impacted

- What actions need to be taken, if any.

- Executive Meeting

A monthly or at least a quarterly executive meeting with executives who are not on the Steering Committee should be held to facilitate open communications.

Link to Change, Issue and Quality Management

As key components of the project control process, the reviewing cycle and structure are closely linked to the other control processes. The direct link to tracking and monitoring has already been discussed.  However, there is also a link to the project’s change and issue management and quality processes.

The formal review process is the main channel for the exchange and recording of project communications. For this reason, it is important to realize that during the planning of each type of review meeting, some element of quality or change management will be included.

Preventing Problems

Risk identification, monitoring and resolution are key tools to successfully completing a project.  Part of controlling a project during the execution phase is to have an established risk management process that is unique to the project. This process is begun as part of project planning and is kept current until the project close-out. The key elements to this process are:

- Creating a central repository for risk information and associated documentation of risk items and resolution strategies

- Summarizing information on a Risk Analysis Worksheet

- Assigning a Risk Manager, which should be either the project manager or a member of the status tracking/reviewing team (this assignment should have been done at project baseline, but definitely by the early days of Execution)

- Including a risk summary in the regular status meetings

- Providing a consistent and ongoing evaluation of risk items and development of risk strategies:

- Identify the risk

- Evaluate the risk and assess its potential impact

- Define a resolution strategy.

What is After Risk Assessment?

The risk control process is started at project planning, is baselined at project startup, and is fully maintained during project Execution.  The key is not the format of the data, but that a plan is developed, baselined, and kept current during the execution phase.

Remember, risks are not events that have occurred, but rather events that might occur that would adversely impact the project.  Events that have occurred and are impacting the project are addressed in either the Change Management and/or Issue Management processes.

The Evolution of Risk Control

As the project evolves through the project life cycle, the ability to define and specify the risk items increases.  This is attributable to the fact that more is known about the project and the associated issues.

- During the execution period, risks are more definitive, and tangible resolution strategies emerge. This allows for the development of realistic contingency plans, including specific action plans.  These actions are then tracked.  The actual format for the risk management plan may need to reflect these activities.  Some projects may, want to show the assignment of a risk item on the risk form.

Risk Monitoring is an Iterative Process

- In all cases, risk analysis is an iterative process that is performed throughout the project.  Risk analysis examines the risk and its potential impact on the project and defines actions to eliminate or to mitigate the impact of that risk, should it occur.

- The process starts with the risks identified in the project plan and the first definition of resolution strategies. There are typically three types of resolution strategies:

- Eliminating or avoiding the specific threat, usually by eliminating the cause.  The project team can never eliminate all risk, but specific risk events can often be avoided through careful planning.

- Reducing the expected cost associated with a risk through mitigation.  This is a mathematical solution to containing the risk impact on a project.  In some ways it can be seen as “insurance.”

- Accepting that a risk will occur and developing contingency plans should the risk event occur.  It can also be expressed by increasing the cost of the budget to some threshold to deal with a specific risk item.

- The risk management process, which is a cyclical and iterative process, includes four overlapping steps:

- Risk identification

- Risk assessment and prioritization

- Risk reduction and contingency planning

- Risk tracking and reviewing

- The risk control cycle is shown below.

- Risk Control Cycle

- Risk Manager

Risk control responsibility is assigned in the planning phase and is documented in the Project Plan.  The risk manager is responsible for ensuring that risk management is performed throughout the project. This person may be the project manager, although in most large projects this is not the most advisable approach. It is primarily a workload issue.

During the planning stage, the functions may be performed by the project manager.  In implementation, risk management may require a separate full- or part-time position to sufficiently handle the workload.

This person should:

- Be senior enough in the project organization structure that they would have the ability to request that specific risk contingency plans be assigned and staffed

- Attend the project management status meetings

- Have an understanding of the overall project.

The identity of the risk manager should be publicly announced and should also be reflected in the project organizational chart.  In most cases, the risk manager will also be fulfilling another management or lead technical role on the project team.  The notation can be in the form of an asterisk or sub-heading.  A risk management box may be assigned, and names will be repeated for different functions.

An example is shown below.  As shown below, some projects update the organization chart to indicate those who will be attending the project status meetings, risk meetings, and change control board meetings.

Risk Meetings

Risk management, of which risk control is part, is a process that involves all members of the project team and occurs throughout the project life cycle.  Risk meetings contribute to the process of identifying risks and developing ways to approach the risks.

- Risk Identification Meetings.  It is during this process that the current risk list is reviewed and updated.

- Executive Review Meetings. A Risk Identification Summary of the top risk items for the project should be included in the executive project status meeting.  Ideally, this should be not more than one page.  It should list the risk, state the recommended resolution, and indicate the current status.

- Project Status Meetings.  The individual responsible for risk should report to the project status group on the current status of project risks.  There should be a written summary, preferably using the actual risk form, including information on all contingency plans currently underway.

Ongoing Risk Identification

The initial list of risks that begins with the project will evolve over time.  To ensure that new risks are added and resolved risks are eliminated, risk identification meetings should be held.  How often this should occur is based on the size of the project and the perception of the project team and key stakeholders as to the degree of risk that exists for the project.  For most projects, monthly or quarterly risk identification meetings are adequate.

The format for these meetings should be open and interactive to facilitate a wide consideration of risk areas.  Some suggestions on meeting format include:

- Brainstorming

- Breakout sessions

- JAD.

The starting point for this meeting is the previous risk list.  The group should be given some ground rules in terms of the degree of risks that will be tracked and ways to eliminate or include risk items.

Current problems are not to be considered, as these are issues for the change and issue management process.

The meeting, depending on the number of participants, may require a leader, facilitator, and note taker.  At a minimum, it will take a leader and a note taker.

From this meeting, the risk manager will have an updated list of risks.  This group assists in the process of prioritizing the risks by determining the probability of their occurrence and the impact the risk could have on the project.  Specific procedures for risk management are defined by the specific project manager and team.

- Do Not Work More Risks Than There Are Staff to Do the Work

Risks must be prioritized to ensure that the key risks are dealt with.  Be careful not to identify so many minor risks that major risks are buried. The basic ground rules for prioritization are:

- There should generally be about 5 to 10 risks being “worked” at any one time.  These should be the risks with the highest probability of occurring.  For very large projects, each subsystem or major activity may be tracking this number of risk items.

- The list of actively monitored risks should generally be no longer than a single sheet.  Keep a separate list of lower priority risks so that they can be reviewed at future risk identification meetings.

- Select the risk items that have the greatest possible impact on cost and/or schedule.

- The prioritization process starts with the group that identified the risk, but also includes the project manager, related stakeholder, and executive management.

It is impossible to give a hard-and-fast rule on what method should be used for prioritization, since this is a process that needs to be driven by the actual project.  As the project team works with risk management, they will get more proficient at knowing what should be considered as the top risk,  which ones need the most attention, and at what time.

EXAMPLE:

For a large database system development project, one risk item is that “the software maintenance staff have not been trained on the database that is being used to develop a major new system.”

This risk item has been ranked high because of the probability of its occurring and the cost to the project if the risk occurs.  All agree that this is an item that must be addressed.

The current project is in the design phase and has an anticipated schedule of nine months.

For a project with few other risks, a contingency plan may be set up whereby the software maintenance staff receive training and participate in development to achieve technology transfer.  In another project with numerous high risk items, this risk item may be moved off the top risk list because there are at least 15 other risk items that, if they occur, will ensure that the project will not make it to maintenance at all.

The conclusion is that, even though risk prioritization and evaluation methodologies are mathematically based, this process is still based on judgment.

Risk Resolution

For the “top risk” items, mitigation/resolution strategies must be developed.  From the steps above, a view of the risk is developed that includes: where, when, and to what extent the risk will impact the project.

With these factors identified, the following options can be considered:

- Eliminating or avoiding the specific threat, usually by eliminating the cause.  The project team can never eliminate all risk, but specific risk events can often be avoided. Eliminating a risk usually involves taking specific action to change a planned event in the project.  That is, if a risk is identified that will occur if the project continues on its current course, the option is to change the course. Risk elimination depends on the extent of change that would be required to the overall project plan, considering the cost to make the change, and the calculated severity of the risk should it occur.  As a general rule, elimination should be pursued when the risk cannot be managed away or it will be costly to the project.

- Reducing the expected cost associated with a risk through mitigation.  This is a mathematical solution to containing the risk impact on a project.  In some ways it can be seen as “insurance.” The area of reducing risk is the most familiar resolution approach used during the planning process.  This is also termed risk mitigation and it involves developing reserves. It is defined as a set aside of project dollars and/or schedule to be used to cover the problems that a risk event would cause.  The reserve can also be a calculated figure as was presented on the form in the Risk Plan.

- Accepting that a risk will occur and developing contingency plans to be executed should the risk event occur?  It could also be in the form of increasing the cost of the budget to some threshold for specific risk items. A risk contingency plan can be developed for the project that defines the actions taken, the resource plans, and the factor(s) that trigger an action, should a given risk occur.  Contingency plans are pre-defined action steps to be taken or if an identified risk event should occur.

- Historical Record

It is always a good idea to maintain a history of the project risks.  This information can be used as “lessons learned,” and the project team can benefit from reviewing past risks and occurrences.

Introduction to Project Tracking and Monitoring

Once a project has advanced to the phase of execution, the consistent reporting on the true status of the project is essential. During Execution, the project team’s and, specifically, the project manager’s focus now shifts from discovery to tracking and reviewing what was said would be done. This information is generally provided in the Status Report package which would include at least the following information:

- Status Reports

- Updates to the schedule -- plan versus actual, generally in the form of Gantt or PERT chart

- Financial Analysis, including the comparison of actual costs versus planned costs and variance measurements, i.e. financial metrics

- Exception Report addressing plan variations.

See the section on Status Reporting later in Section 5 for more detail of information to be included in a Status Report package.

The Project Plan as the Road Map

To begin the tracking process, the project plan serves as the starting point. The recommendations contained in this document serve as the minimum set of planned elements that are to be tracked and monitored over the lifetime of the project. This list should be augmented and tailored for each specific project.

It should be noted that part of the planning was to acknowledge which elements were to be tracked and how often they were to be tracked. Thus, the planning process dovetails with the tracking process to provide a practical, workable method to evaluate where a project stands at a given point in time with regard to the initial baselined plan.

The concept of a perfect plan is an illusion.  Plans are living documents that change as the environment of the project changes. In the new world of information technology, success is dependent on strategies, project resources, and people.  Focus should be on monitoring and directing these dynamic elements and not on hard-and-fast precepts.

The Project Plan as the Baseline

The key elements that are needed for tracking include:

- Scope of Work including project objectives

- Project Functional Specifications

- Success factors

- Work Breakdown Structure (WBS) -- activity list and activity network

- Work packages

- Budgets and Estimates, along with the assumptions 	on which they were based

- Master and supporting schedules

- Financial and funding plans

- Quality and Configuration Management Plans

- Staffing plan

- Spending plan.

Even very large projects can be controlled well if adequate time is spent planning, tracking and monitoring.

Why Tracking and Monitoring?

The management functions of tracking and monitoring are indispensable to the effective and efficient control of the project.  In this methodology, tracking is defined as the fact-finding processes, and monitoring is the analysis of these facts. Both are needed for the management of the project.

Control processes are established not to determine what has happened, but rather to predict and manage what may happen in the future.

Each project team consistently compares planned and actual

performance to answer the fundamental question:

--------------------------

How is the project doing?

Information generated during the tracking and monitoring processes forms the basis for reaching a judgment about the project status and whether corrective action is required. It also allows the project team to answer these specific questions:

- General

- Where is the project on schedule, cost, technical performance, objectives, and goals?

- What is the status of activities that were to be completed?

- How does this status impact future project 	activities?

- What is going right on the project?

- What is going wrong?

- What opportunities are emerging?

- Are the project stakeholders comfortable with the results of the project?

- Organization

- Is the project team an effective and suitable organization?

- Does the project manager have adequate control and authority?

- Have key roles been defined in the project?

- Are the project team personnel innovative and creative by suggesting project management improvements?

- Does the project team get together on a regular basis to see how things are progressing?

- Does the project have an efficient method for handling change requests?

- Does the project team seek the advice of stakeholders on matters of mutual concern?

How and What is to be Tracked?

A key management issue in every project is to develop processes that provide critical information without becoming a burden and taking on a life of their own.  Many think this is only an issue in large projects, but small projects share equally in the problem because they typically lack the necessary resources to do many of the management functions.

Just as in the planning process, the project manager walks a fine line to achieve the correct level of detail.  As a general rule of thumb, most tracking materials should be by-products of execution of the project.  The level of detail about the project should decrease as the information is moved up through the project organization.

- For example:  A two-page status report from each of the major project teams within the software area should be reduced to a two-page report from the full software area that is given to the project manager. In turn, the project manager takes reports from all the major activity areas and reduces the report down to one executive report of five to ten pages. This process can be automated through enterprise tools or by simply using word processing and electronic mail. It can even be a manual process.

"How and what is to be tracked” is a very important question and one not to be taken lightly. The project manager should focus on putting in place the most critical parts of tracking and monitoring, and then add additional items to track as necessary, based on the complexity of the project.

Tracking and monitoring means focusing on the following kinds of issues:

- Status – current activities and planned activities.

- Comparing the planned schedule to the actual progress and determining the current position. This analysis may be done at the top levels of the Work Breakdown Schedule for reporting, but may also be done at the actual task level for determining work activities. Key items are:

- Tasks planned and actual start/finish dates.

- Project actual start/finish dates.

- Impact on overall schedule.

- Comparing the planned budget with the actual expenditure. The tracking and monitoring processes should generate:

- Actual expenditures to date.

- Estimate to Complete (ETC).

- Estimate at Completion (EAC).

- Burn Rate (in either hours or dollars).

- Adjusted baseline after replanning.

- Technical performance and quality indicators from each developmental stage of the project.

When Should Tracking be Done?

The frequency of the various tracking and monitoring activities will vary with the specific element and the amount of detail needed and should complement the various reviewing processes of the project.

The frequency of tracking activities should be noted on the master schedule for the project and possibly summarized in a project tracking matrix.  A sample matrix for a project is provided below.

- Project Tracking Matrix

| Tracking Activity | - Recommended Frequency | Automated Tools** | - Remarks |
| --- | --- | --- | --- |
| Updated Project Milestone Schedule | - Status Report - Qtrly, Milestone, or Phase Completion Reviews | MS Project Timeline FastTrack | - GANTT chart preferred - Save copy of previous month's chart - Include task completion dates |
| Updated Work Product Identification | - Status Report - Qtrly, Milestone, or Phase Completion Review - As deliverable dates change | Automated project database | - Provide updates to database manager |
| Updated Estimate at Completion (EAC) | - Status Reports - As required when ahead or behind schedule - Qtrly, Milestone, or Phase Completion Reviews | MS Project (Estimating add-in) Excel Lotus | - Get task leaders to cost out subtasks - Include project costs to date |
| Updated Detailed Financial Status | - For Qtrly, Milestone, or Phase Completion Reviews - As required when ahead or behind schedule | Visibility MS Word | - Labor hours awarded vs. labor hours expended - Dollars awarded vs. dollars expended |
| Updated Planned vs. Actual Spending Profile | - Status Reports | Excel Lotus | - Visual overview for upper management |
| Updated Staffing Profile | - Status Report - For Qtrly, Milestone, or Phase Completion Reviews - As work product deliverable dates change | MS Project | - Are there unacceptable peaks and valleys? |
| Updated Resource Loading | - Status Report - Qtrly, Milestone, or Phase Completion Reviews - As deliverable dates change | Excel | - Validate need for resources |
| Updated Risk Identification | - Status Report | MS Word Automated project database | - Update risk matrix - Is risk mitigation required? - Has a risk materialized? |
| Updated Work Packages | - As required when work package is completed, rescheduled, or changed | MS Word Automated project database | - When requirements change - Change Control List for Details |
| Updated Project Requirements | - As required when requirements have been approved for change | MS Word Automated project database | - Contract modification - Change Control List for Details |
| Updated Quality Project Plan | - As required - Quarterly - For Qtrly, Milestone, or Phase Completion Reviews | MS Word MS Project MacProject | - Use baselined plan |
| Updated Configuration Management Plan | - As required when ahead or behind schedule - Status Report - For IPR | MS Word MS Project MacProject | - Use baselined plan |
| Updated Action Items | - As required - For weekly/ bi-weekly status meetings | MS Word Automated project database | - Tracked until resolved - Issue Resolution List for details |
| Updated Corrective Action Items | - As required - Status Report | MS Word Automated project database | - Tracked until resolved |

** Listing as part of this sample matrix does not imply an endorsement by ITEC for use. The state organization should use tools that have been defined within their organization as standard and/or which best meet the automated support requirements of the project.

Activity and Schedule Tracking

A large part of the tracking and monitoring process is knowing the project’s status.  The only way to determine this is to:

- Review what activities were planned

- Determine that the work has been done to complete these activities

- Analyze whether the level of work is consistent with the level of effort that had been planned

- Compare this to the planned start and finish dates

- Determine if adjustments are needed for this activity

- Analyze if any required adjustments impact other tasks.

There are numerous ways to collect, analyze, and present this information. Two methods are presented here: Activity Tracking Table and Updated Project Schedule. For large, complex projects that have an involved activity network, additional levels of analysis and mathematical models would be needed. These tools should be used first to generate the project schedule during planning and should then continue to be used to track the schedule.

As can be seen in the Activity Tracking Table shown later in this section, a number of key tracking and monitoring activities are reflected. Included in the activity tracking table are:

- WBS number.  This should be the activity’s WBS number that was assigned during plan development or the number assigned at replanning.

- Activity Description.  This is a brief narrative on the activity.

- Dependency.  This would apply if the project reflects activity dependency, meaning one task cannot start and/or finish without the completion of another task.

- Owner.  This should be the person who is responsible for updating the status on the task. It may or may not be the actual task manager.

- Planned Schedule.  This information was generated as part of Project Planning. It would represent what was originally thought to be the number of days an activity would take, as determined by the date that the master activity list was generated. The second element of the activity in a bigger project schedule would show when the task would start and end, based on the duration.

- Duration.  For the purposes of scheduling, duration should be in days, not hours. Hours are more of a financial element since they reflect the level of commitment and not the time. In other words, the purpose of the information in this table is not to show the number of people and hours being spent on a task (effort), but the actual time it will take.

- Actual Schedule.  This information is completed as the activities are completed. Note that some of the 2.0 activities have no information filled in. This is because these tasks have not yet been completed. The current example shows that the design team is on Task 2.2.1.

- Target schedule.  This the planned schedule, plus the actual, with adjustments based on new project knowledge. In this example, the design of the project was to take 90 days. The current tasks have taken 15 days more than had been anticipated. During the planning phase, the project manager allowed a few days “float” in the design as a reserve for schedule risk.

During the process of establishing the project target, the project team now reviews the outstanding tasks and determines:

- Can the 15-day schedule slippage be made up in the other tasks? If so, where?

- Can the other tasks still be completed in the length of time planned? If so, where are additional adjustments required?  In this example, one of the two activities could be completed in less time, and one activity would require more.

To complete the projection for tasks that have not been started:

- Try to preserve “float” wherever possible.

- Ensure that logical discrepancies do not occur by attempting to override dependencies.

- Work up to the task level from the details.  If an automated planning tool is being used on the project and a critical path has been established, the system will prevent the user from overriding the dependencies in the schedule.

- Activity Tracking Table

| WBS | Activity Description | Depend | Owner | Planned Schedule |  |  | Actual Schedule |  |  | Target Schedule |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Start | Finish | Dur. | Start | Finish | Dur. | Start | Finish | Dur. |
| 2.0 | DESIGN | 1.0 | Brown | 4/1/96 | 7/1/96 | 91 | 4/1/96 | 7/1/96 | 91 | 4/1/96 | 7/5/96 | 95 |
| 2.1 | Prepare Preliminary Design |  | Brown | 4/1/96 | 5/1/96 | 30 | 4/1/96 | 5/15/96 | 45 | 4/1/96 | 5/15/96 | 45 |
| 2.1.1 | Develop Enterprise Architecture |  | Brown | 4/1 | 4/10 | 10 | 4/1 | 4/10 | 10 | 4/1 | 4/10 | 10 |
| 2.1.2 | Prepare Data Flow Diagrams |  | Brown | 4/10 | 4/20 | 10 | 4/10 | 4/20 | 10 | 4/10 | 4/20 | 10 |
| 2.1.3 | Prepare Logical Data Module |  | Brown | 4/20 | 5/1 | 10 | 4/20 | 5/15 | 25 | 4/20 | 5/15 | 25 |
| 2.2 | Prepare Detailed Design | 2.1 | Brown | 5/5 | 6/1/96 | 26 | 5/15 |  |  | 5/15 | 6/5/96 | 21 |
| 2.2.1 | Prepare Physical Data Model |  | Brown | 5/5 | 5/25 | 20 | 5/15 | 5/31 | 15 | 5/15 | 5/31 | 15 |
| 2.2.2 | Prepare Data Dictionary |  | Brown | 5/25 | 6/1 | 6 | 5/31 |  |  | 5/31 | 6/6 | 7 |
| 2.3 | Document Design | 2.2 | Brown | 6/1 | 6/28/96 | 28 |  |  |  | 6/6 | 7/2 | 27 |
| 2.3.1 | Develop Design Specification |  | Brown | 6/1 | 6/28 | 28 |  |  |  | 6/6 | 7/2 | 27 |
| 2.4 | Design Review | 2.3 | Jones | 6/30/96 | 7/1/96 | 2 |  |  |  | 7/3/96 | 7/5/96 | 2 |
| Comments: All activities that are not meeting planned dates need to define: reason, approach to bring into conformance, and impact. |  |  |  |  |  |  |  |  |  |  |  |  |

Once the Activity Tracking Table is completed, the project manager can prepare a graphical presentation of this information. If an automated tool is being used, this graphic will be automatically generated. In most cases, the project manager has a choice in the graphical representation. At a minimum, it should be shown as a GANTT chart, as illustrated in the next figure. For this example, planned dates and duration are still shown on the schedule, even though the task has been completed.

The objective of tracking and monitoring is to preserve the original schedule (baseline) for comparison. In the above sample, the actual schedule is reflected for all those tasks completed. For tasks still open and ones that have not been completed, the new target schedule is reflected.

- Project Schedule Update

- Note:	Gantt charts can also include information on elapsed time, work hours, dependencies, staffing and other related project information.

- Monitoring

As is graphically presented below, the project monitoring process is an interactive part of tracking and is firmly tied to project planning. Project monitoring takes the outputs of tracking and uses them to determine planned versus actual.

- Project Monitoring

Planned Versus Actual Costs

The basic consideration underlying all the elements of monitoring is “planned versus actual.” When the project manager completes this comparison, he/she then evaluates whether the existing plan can continue to be used, whether the activities can get back on plan, or whether the project (in whole or in part) has deviated significantly from the plan.

Cases where actual progress and projected progress differ significantly suggest the need for replanning, which would include updated project budgets. To determine what is “significant” deviation from the plan, a number of standards can be used. Kansas statutes (KSA 75-7201 et seq.) state that if a project in total is 10% over budget, then the overrun must be reported.

The actual state organization and/or project can develop additional standards for determining “significant,” although these should not conflict with the statutory definition.

- Cost Determination

Budgets for each task should be simple and directly related to a specific WBS task. Comparing performance to plan can be difficult when the work cannot be quantified.

The way to measure progress is through estimation and completion of tangible products or milestones. First, tasks during the planning cycle should be broken down into activities to permit progress to be monitored fairly frequently. Second, tangible deliverables should be used as signposts to show progress.  For example, in a software development project, printed code is one element of evidence.  Budget updates are obtained from the people responsible for managing the work efforts.

Cost of performing a task is directly related to the labor assigned to the task, the duration of the task, and the cost of any non-labor items required by the task.

To develop updated costs and account for actuals, the project manager needs to review:

- Labor costs.

- Non-labor costs.

- Other expenditures.

Estimating how much more time the task requires takes still remains the single most difficult part of deriving updated cost estimates.

In calculating the cost of labor, costs must be burdened appropriately.  Burdened cost typically refers to the overhead and general expenses that are beyond strict salary associated with an employee.

Non-labor charges include such items as material costs, reproduction, travel, cost of capital (if leasing equipment), computer center charges, and equipment costs.

- Update the Cost Model

Actual labor and non-labor cost information is compared to the numbers used to develop the plan.  Spreadsheets work well for projects of small to medium scope.  For large systems, a project management tool is typically preferred for cost estimation.

Within the system, costs are assigned and estimates updated at the lowest level WBS work package task.  These costs are then combined to determine a sub-task cost, and in turn, are combined to determine the overall task cost, which can be summed to find the total project cost.

Document Assumptions

It is essential to document all assumptions made while planning and updating the project budget. Not only can it greatly impact the later success of the project, but the lack of such documentation can jeopardize the successful tracking to the budget.

If, for example, a budget assumed that a staff member would be available at a defined rate, but only substantially higher paid employees are available to perform the task, there will be a budget problem.

Review the Cost Estimates

Updates to budget are best developed by more than one person.  Rarely does a single individual have the knowledge and understanding of all the factors affecting every aspect of a project.

Project managers have a choice in how they track (and report) project financial data.  The basic financial tracking method is to prepare an Estimate at Completion (EAC) Summary Report.

Each project creates an EAC in the planning phase to identify the costs associated with each of the project's high level WBS elements, thereby developing an overall budget for the project.

Another financial tracking method is to maintain financial metrics.  Projects that prepare monthly reports for a customer would be more likely to have a need to maintain financial metrics.

Finally, many projects can obtain useful financial status by generating a planned vs. actual spending profile graphic.  This method is particularly useful for presentations to upper management because of its visual impact.   The spending profile, as shown on the following page, can show in a glance what is happening with the project's costs.  Creating these profiles is one of the many tracking options available to project managers.

- Spending Profile

Estimate at Completion (EAC) Summary Report

Although applicable to all projects, an EAC  periodically determines the expected total cost of the project at project completion.  Projects, particularly large projects, suffer cost overruns due to inadequate estimating procedures and overlooked items.

The EAC provides:

- An historical baseline of the budget.

- A disciplined process for obtaining inputs.

- A means of allocating and tracking budgets to manageable sizes.

- A library of metrics that can be updated with actuals throughout the life of the project for use on similar projects.

The EAC is an assessment of the total effort required to complete each contract task.  It estimates the amount of effort required to complete each WBS element and adds that estimate to the costs incurred to date to derive the anticipated cost of each WBS element at project completion.   A possible process for budget updates is detailed below:

- Estimate hours and other direct costs for each WBS element.

- Calculate the estimated remaining cost by entering the remaining effort/activity needed into a task cost spreadsheet.

- Add costs incurred to date.

- Sum the task leader estimates and the costs to date to derive an EAC for each WBS element.

- Sum the EACs for each WBS element to derive an EAC for the overall project.

- Determine the actual amount of funds available to the project.

- Compare the EAC to total funds available to the project.

- If the total available funds are less than the estimated total cost, then:

- Re-cost the project, and

- Eliminate unneeded or excessive requirements until the remaining estimated cost is within the bounds of the remaining funds, or

- Advise executive management that current estimated scope of work for the project is greater than initially estimated.

At a minimum, a full EAC should be done at each major milestone and for all major contractual changes.

# Sample Estimated Cost at Completion Summary

| Analysis in Hours |  |  |  |  |  |  |  | Analysis in Dollars |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| WBS No. | Activity Description | Budget Hours | Actual Hours | Est. to Complete | Est. @ Complete | Variance (+ = More) | Budget $ |  | Actual $ | Est. to Complete | Est. @ Complete | Variance (+ = More) |  |
| 1.0 | Define Requirements | 430 | 600 | 0 | 600 | 170 | 17,780 |  | 26,000 | 0 | 26,000 | 8,220 |  |
| 2.0 | Prepare RFP | 572 | 500 | 50 | 550 | (22) | 22,880 |  | 17,000 | 1,900 | 18,900 | (3,980) |  |
| 3.0 | Issue RFP and Evaluate Vendors | 433 | 100 | 433 | 553 | 120 | 17,320 |  | 4,300 | 14,200 | 18,500 | 1,180 |  |
| 4.0 | Close-Out | 72 | 0 | 72 | 72 | 0 | 2,880 |  | 0 | 2,880 | 2,880 | 0 |  |
|  | TOTAL | 1,507 | 1200 | 555 | 1,775 | 268 | 60,860 |  | 47,300 | 18,980 | 66,280 | 5,420 |  |

The financial information included in an EAC provides most of the budgetary numbers needed.  What varies is the method by which the estimates to complete and at completion are done.  Three variations on EAC are shown below:

EAC = Actuals to date plus the remaining project budget modified by the performance factor, often the cost performance index developed as part of an Earned Value method of estimating.

EAC = Actuals to date plus a new estimate for all remaining work. This approach is most often used when past performance shows that the original estimating assumptions were fundamentally flawed, or they were no longer relevant due to changes within the project environment.

EAC = Actual to date plus the remaining budget.  This approach is most often used when current variances are seen as atypical and the project management team’s expectations are that similar variances will not occur in the future.

Beware of the Trap to Report More Progress than has been Achieved.

Financial Metrics

The following steps provide additional financial metrics that can further assist in determining if the project is “really” on schedule.

This financial data, however, should not be used in isolation.  Variance and earned value calculations are recommended to supplement the project manager’s information.

- Budgeted Cost for Work Scheduled (BCWS), the budgeted cost for work scheduled to be accomplished, plus the planned effort or apportioned effort scheduled to be accomplished in a given period and the level of effort budgeted to be performed.  In other words, BCWS represents the plan that is to be followed.  BCWS, as well as BCWP and ACWP can be calculated for any time period.  However, cumulative totals balance out previous time period fluctuations.

- Budgeted Cost of Work Performed (BCWP), the budgeted amount of cost for completed work, plus budgeted for level of effort or apportioned effort activity completed within a given period of time. This is sometimes referred to as “earned value” and is a measure of work accomplished during a given period.  Think always of BCWP as what you got for the effort expended.  Tasks may be classified either as discrete or level of effort. If discrete, no credit is given for completing a task until it is done.  If a task is level of effort, BCWP = BCWS.

- Actual Cost for Work Performed (ACWP), the amount of cost actually expended in completing the work accomplished within a time period, plus the apportioned cost for level of effort activities.

- Calculate the Cost Variance (CV) by subtracting ACWP from the BCWP.  A negative cost variance means that the project is spending more than it should.

- CV = BCWP - ACWP

- Calculate the Schedule Variance (SV) by subtracting BCWS from BCWP.  A negative schedule variance means the project is behind schedule.

- SV = BCWP - BCWS

- Calculate the Cost Performance Index (CPI) by dividing BCWP by ACWP. The CPI is the cost efficiency factor representing the efficiency of work performed. The remaining budget of the project divided by the cumulative CPI is one approach to calculate the revised EAC total.

BCWP

ACWP

CPI =

- Calculate the Schedule Performance Index (SPI) by dividing BCWP by BCWS. The SPI represents the schedule efficiency of work performed.

BCWP

BCWS

SPI =

- Calculate the Critical Ratio by multiplying the CPI by the SPI.  If the Critical Ratio is between .9 and 1.2, the task or group of task begin analyzed is probably OK.

BCWP

ACWP

BCWP

BCWS

- Critical Ratio = SPI X SPI 	or	X

Calculate the Percent of Work Complete by dividing the Cumulative BCWP by the Budget at Completion.

BCWP

Budget at Completion

% Complete =

Calculate the Percent Spent by dividing the cumulative ACWP by the Budget at Completion.

ACWP

Budget at Completion

% Spent  =

These variances can then be plotted graphically and over time to show how the project team is doing.

Resource Loading Updates

Updating the project resource plan is an important tracking event since shifts in this plan can cause performance, cost, and schedule problems.  The staffing plan showing the number of personnel, by type, that were required on the project was developed as part of the planning process.  As part of tracking, this information is compared monthly on a planned versus actual basis. Periodically, the project manager also validates whether these planned resources are still sufficient to complete the task on schedule and within budget given changing conditions.

Updating projected resource loading and staffing profiles, as shown below, helps the project manager adjust to these changing conditions by refining the estimated effort to complete the project, validating the continuing need for resources and identifying problems early in the project.  By identifying and analyzing discrepancies, the project team can determine if adequate resources are being applied to the project and can get early indications that the project is falling behind schedule or is more complex than initially estimated.

- FTE Resource Loading

| POSITION | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SW Mgr | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Sr. SW Eng. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| SW Analyst | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1 | 1 |
| Programmer |  |  | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 |
| Config. Mgr |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Tech Writer | 0.5 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |
| Support | 0.25 | 0.5 | 0.5 | 1 | 1 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 1 | 0.5 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |
| PLANNED | 3.75 | 4.5 | 7 | 8 | 8.5 | 7.25 | 7.25 | 7.25 | 7.25 | 7.25 | 8.5 | 7 |
| POSITION | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |
| SW Mgr | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Sr. SW Eng. | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| SW Analyst | 1 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Programmer |  |  | 2 |  |  |  |  |  |  |  |  |  |
| Config Mgr |  |  | 1 |  |  |  |  |  |  |  |  |  |
| Tech Writer | 0.5 | 1 | 1 |  |  |  |  |  |  |  |  |  |
| Support | 0.25 | 0.25 | 0.5 |  |  |  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |
| ACTUAL | 3.75 | 4.25 | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

- This same information can be graphically presented on a timeline with actuals compared to planned.

- Staffing Profile

Lastly, this information can also be represented in a bar chart as shown in the next table so that actual monthly can be tracked as opposed to trends.

- Monthly Staffing Profile

Executive Review

A standard requirement of all projects is to provide reports to the Steering Committee, the project team and executive management.  At a minimum, the frequency of the reports should correspond with the meetings that are scheduled.

The information shared in the report should be in a consistent format throughout the project.  The types of reports that a particular agency uses will vary.  A general rule of thumb is that the detail should be kept to what can be explained during a Steering Committee Meeting.  If more details are needed to clarify issues, then these should be provided as supplementary data.

Steering Committee

Status reports are produced by key project team members. These team members should know what areas of execution they are responsible for.  Status reporting is an integral part of the project management processes.  It is the means by which the stakeholders stay informed about the progress and key activities required to successfully complete the project. The purpose of the status report, like the status meetings, is to develop a standard format for the formal exchange of information on the progress of the project. The status reporting process can be graphically represented as:

##### Project Tracking and Reporting Process

The status report package should be prepared by the project team detailing activities, accomplishments, milestones, identified issues, and problems.  Some level of recovery plans should be prepared for activities that are not on schedule and abatement plans prepared for anticipated problems.

Other information to be included in a status report package includes:

- Status Report form which include significant accomplishments for the period and scheduled activities

- Updated GANTT charts

- Recovery plans for activities not on schedule defined by the project team as being late, (e.g. slippage in the critical path activities)

- Updated Risk Management Worksheet

- Abatement plans for expected problems

- Resolution to assigned action items and issues

- Updated Project Tradeoff Matrix and Status Summary

- Updated WPI

- Updated Estimated Cost at Completion

- Updated Staffing Plan with actuals

- Updated Activity Tracking Table

- Change Request

- Financial Metrics

- Exception Reports addressing plan variations, e.g. crashing tasks, explaining cost overruns.

- Independent Reviews

An important part of project evaluation is done by conducting an independent quality control or oversight review.  For medium to large IT projects, the ITEC framework requires that project oversight reviews be done on a schedule consistent with the size and risk of the project.

Many state organizations are moving to the process of oversight reviews to augment their standard tracking process.  These reviews provide the opportunity to have an independent appraisal of where the project stands and the efficiency and effectiveness with which the project is being managed. The independent reviewers are interested in the project’s processes rather than the project products.

The purpose of the audit procedure is to ensure that the project plans are being adhered to and that any identified problems or deficiencies are resolved in a timely manner.

A sample independent review process is defined below.

- Review each engineering effort at least once during each phase.

- Review the project as required for conformance to the applicable Project Implementation Plan, Software Development Plan, QA Plan, etc.  This review includes the CM and data management process, the use of methodologies and tools identified in the project plans, the peer review process, and the walk through process.

- Provide a summary report of each audit to the Project Manager. This report should clearly identify any deficiencies or problems encountered during the audit.

- For projects with problems or deficiencies, work with the Project Manager to ensure that a plan is implemented to resolve the problems/deficiencies and schedule follow-up audit to make sure that the problems/deficiencies have been resolved. If appropriate, the oversight report should be shared with the Project Sponsor.

- Independent audits work only if follow-up actions are taken to resolve any problems or deficiencies identified by the audits.

- Periodic Updates

As shown in the Tracking Matrix earlier in this section, other tracking and monitoring activities may occur on a different frequency than the financial, budget, and status activities.  Some of the periodic tracking processes are listed here.

- Updating a Project's Work Packages

Each project identifies a series of work packages for specific work to be accomplished. Work packages are generally created to cover a specified subset of the project's overall requirements and are updated as project requirements change or as additional requirements are developed.  It should be noted that work packages are tracked until completion.   The project team should update the following areas each time a work package is completed, rescheduled, or changed:

- Work package description

- Person responsible for the work package

- Start date

- End date

- Dependencies

- Updated requirements.

- Updating Project Requirements

In the planning phase, each project must identify the requirements that the project intends to satisfy.  This process may result in the creation of a matrix that lists consolidated requirements. Like the work package, once identified, project requirements are tracked until completion.

Based on the change control processes, project requirements only change as a result of written notification and thorough review.  Hence, project requirements will be updated as part of the change control process.

- Updating the Quality Project Plan

A Quality Activities matrix that lists project specific quality-related activities is required for each project.  This matrix is initially developed in the project  planning phase and is updated as  project requirements  change or as additional requirements are developed.  The project team shall update the Quality Activities milestone schedule, as necessary, by:

- Adding or deleting quality activities

- Providing actual or revised quality activity completion dates as the project progresses.

- Updating the Configuration Management Plan

A Configuration Management Activities matrix that lists project specific CM-related activities is included in the project plan.  This matrix is initially developed in the project planning phase and is updated as project requirements change or as additional requirements are developed.  The PM shall update the CM activities schedule, as necessary, by:

- Adding or deleting CM Activities.

- Providing actual or revised CM activity completion dates as the project progresses.

SECTION 5

PROJECT EXECUTION - PM ELEMENTS

INTRODUCTION	1

What Happens During Project Execution?	1

Project Control Process	2

Preventing Problems is Better than Fixing Them	4

APPROVAL PROCESS	5

What is the Approval Process?	5

Contractor Payments	5

CHANGE AND ISSUE MANAGEMENT	9

What Happens During Project Execution?	9

You Can't Manage What You Don't Control	9

What is Change Management?	10

The Change Control Form	12

Phase 1 - Requester Information	12

Phase 2 - Initial Review of the Change Request	12

Phase 3: Initial Impact Analysis	13

Phase 4: Final Review Results and Change Priority	13

What is Issue Management?	13

The Issue Resolution Form	15

Phase 1 - Requester Information	15

Phase 2 - Initial Review of the Issue	15

Phase 3: Tracking	16

Phase 4: Final Review Results and Change Priority	16

CORRECTIVE ACTIONS	17

The Best of Plans can go Wrong	17

Where Problems Come From	17

Fix the Problem	18

Recovery Plan	18

PROJECT REVIEWING	19

Review Process	19

Informal Review Process	19

The Status Review	20

Team Meetings	20

Purpose of Meeting	22

Process for Meeting	23

Ground Rules for Status Meetings	23

Executive Meeting	23

Link to Change, Issue and Quality Management	24

RISK MONITORING AND MITIGATION	25

Preventing Problems	25

What is After Risk Assessment?	25

The Evolution of Risk Control	26

Risk Monitoring is an Iterative Process	26

Risk Manager	27

Risk Meetings	28

Ongoing Risk Identification	29

Risk Resolution	31

Historical Record	31

TRACKING AND MONITORING PROJECT PERFORMANCE	32

Introduction to Project Tracking and Monitoring	32

The Project Plan as the Road Map	32

The Project Plan as the Baseline	33

Why Tracking and Monitoring?	33

How and What is to be Tracked?	34

When Should Tracking be Done?	35

Activity and Schedule Tracking	37

Monitoring	40

Planned Versus Actual Costs	41

Cost Determination	41

Update the Cost Model	42

Document Assumptions	42

Review the Cost Estimates	42

Estimate at Completion (EAC) Summary Report	43

Financial Metrics	45

Resource Loading Updates	47

Executive Review	49

Steering Committee	50

Independent Reviews	51

Periodic Updates	52